# 4-H, CYFAR  / Daly City, Daly City Partnership

# Playground Build Matrix

# PJ- 01548

# Build Site:

Westlake Park- 111 Lake Merced Blvd- Daly City, CA  94015

Build Day:

Tuesday, May 4th 2010

KaBOOM! Team

Project Manager:  Katie Morgan 	Cell: 650-670-0416 		 Kmorgan@kaboom.org

KaBOOM! Team: Melanie Barnes, Jorge Contreras, Javier Gomez

### 4-H :

Marilyn Johns   mjjohns@ucdavis.edu 650-380-0268

Keith Nathaniel       kcnathaniel@ucdavis.edu   213-618-1305

Daly City:

### Mike Stallings 		 mstallings@dalycity.org

Denise Brown		  dbrown@dalycity.org  		650-740-4531

Daly City Partnership:

Patricia Bohm 		  pat@dcpartnership.org  		650-438-9335

### Installer:

Bill Bagshaw

Tractor Operator:

Daly City- Mike Stallings

### PlayWorld Systems

PSI Contact:  Julie Rearick

Office: 570.522-5332

Playground Equipment Delivery

Delivery Date:  Saturday, May 1st

Cal-Ex: Eddie: 570-603-0180 x 223

The Home Depot Materials Delivery

Delivery Date: Saturday, May 1st

Contact:  Tom, Westlake store

Surfacing: Fibar

Delivery: Saturday, May 1st

Contact: Joy Dunn, 800-269-1669

Site Prep Schedule

Saturday May 1st 2010  - Site Prep Day 1

| Time | What | Who | Tools |
| --- | --- | --- | --- |
| 7:00 am | KaBOOM! arrives on site to inventory materials | Katie/Melanie from KaBOOM! | Smiles, to do lists |
| 7:45 am | Layout site Breakfast Set Up | KaBOOM!, Installer Bobcat Operator on site | Site plans, footing diagram, tape measure, marking paint, string line |
| 8:00 am | Volunteers arrive/ Breakfast and Welcome | Volunteers |  |
| 8:30 – 10 am | Equipment delivery, unloading and inventory Playground, THD order, Mulch | KaBOOM!, Volunteers | snips, utility knives, markers, equipment specs, storage container |
| 12–12:30 pm | Lunch | KaBOOM!, Volunteers | Lunch!! |
| 12:30–1:30 pm | Mandatory Build Captain Training | KaBOOM!, Build Captains | Sample bucket (or bag), tool belt, Build Captain vest, 3D and other hand outs |
| 1:30 PM | Registration Team Meeting | KaBOOM!, Registration Volunteers | Registration Bucket |
| ALL Day | Work on tasks below | KaBOOM!, Volunteers, BC, Installer |  |

Tasks to be completed

|  | Inventory Playground Delivery |  | Review PG layout with installer |
| --- | --- | --- | --- |
|  | Inventory THD Delivery |  | Finalize designs for plywood |
|  | Draw Build Captain Posters *use cardboard from PG pieces, also make posters for recycling containers |  | Check water source and hose, electricity source and extension cords |
|  | Make nametags and organize registration materials |  | Finalize Garden Area- layout, plants |
|  | Dig/Transit playground holes |  | Drill holes in plywood cutouts |
|  | Sort and label PG hardware into buckets/bags/boxes |  | Wood Projects (Cut/Check/Store) 7 deck benches, plywood cut outs, garden signs |
|  |  |  | Organize everything for youth activities |
|  |  |  | Power Sand metal fence and metal benches |
|  | Make Tool Belts |  | Inventory and label ALL tools |
|  | Organize Safety materials |  | Make Home Depot List |
|  | Finalize Paint/Concrete station |  | Finalize site map |

Monday May 3rd  2010

| Time | What | Who | Tools |
| --- | --- | --- | --- |
| Morning | Errands to Party Store, The Home Depot, etc | KaBOOM! |  |
| BC TRAINING |  |  |  |
|  | Site Walk, double check everything! | KaBOOM!, | Site Map, Build Matrix |
| All Day | Complete anything necessary | KaBOOM! and Volunteers if necessary | TBD |

Build Day Schedule

##### Tuesday, May 4th 2010

| Time | What | Who | Tools |
| --- | --- | --- | --- |
| 6:15 am | KaBOOM! and others arrive on site | Katie, Melanie, Javier, Jorge | Smiles |
| 6:30 am | Build Captains arrive on site |  |  |
| 6:30 am | Equipment moving and sorting | KaBOOM!, Build Captains | Equipment, hardware, tools, team lists |
| 7:00 am | # Planning Team set-up: - Food - Registration area - DJ - Construction area - Safety area - Children activities area | KaBOOM!, Build Captains, food and registration volunteers, Planning Committee Members | - Food – food, tables, chairs - Registration – 2 tables, 4 chairs, KaBOOM! balloons, tent - Construction – table w/ toolbox, tools & materials - Safety – table, chairs, tent - Children – tables, materials |
| 7:30 am | # Breakfast & Registration open | Food/Registration Committees | ______________ |
| 8:00 am | # DJ and PA system set up- music starts playing | PA system contact info_____ | Extension cords, Tent/tables? |
| 8:00 am | Build Captain Meeting | KaBOOM!, Build Captains | Build Captain posters, flare, site maps- In Storage container |
| 8:00 am | Volunteers arrive, register and eat breakfast | Registration volunteers and food team | Volunteer waivers, nametags, pens, food, raffle tickets |
| 8:30 am | Kick-Off | KaBOOM!, CYFAR/4-H, Daly City, DC Partnership Speakers | Run Of Show, PA system, DJ, camera |
| 8:50 am | Deployment of volunteers and Playground construction begins | KaBOOM!, Build Captains, Volunteers | Team posters, Specs, hardware, tools, playground equipment, music |
| 11:30-12:30 pm* | LUNCH (in shifts) | Food team, all volunteers | Appetites, food |
| 12:45 pm* | Push moving mulch/concrete/side projects | Volunteers |  |
| 2:00 pm* | Complete playground (Collect tools & clean up) | KaBOOM! and Volunteers | specs, hardware, team tool kits |
| 2:30 pm | Playground Board Cutting Ceremony | KaBOOM!, Daly City, DC Partnership, CYFAR Speakers | Agenda, board, hand saw, camera, PA system |
| 3:00* pm | Remaining projects and cleanup | KaBOOM!, Build Captains, Volunteers | Complete task list below |
| * Times are estimated. |  |  |  |

### Tasks to be completed

|  | ### Recycling and Trash collected and sorted |  | ### Paint and Concrete areas cleaned |
| --- | --- | --- | --- |
|  | ### All tools collected and placed in storage and sorted |  | ### Toolbox sorted |
|  | ### Build Captain Vests, tool belts collected |  | ### 2 Build observation guides |
|  | ### Completed site photos |  | ### Caution tape PG |
|  | ### Take down stage area/ barricades etc. |  | ### Sorting tools (water, waste water and parks) |
|  | ### Rivet Structure |  | ### Check all bolts |
|  | ### Wash out all wheelbarrows |  | ### Collect site banners |

### 4-H, CYFAR/ Daly City, Daly City Partnership

Build Day Team Assignments

| ## Team | Vol min | Vol max | Project | In Tool Belt | Build Captain | Sticker |
| --- | --- | --- | --- | --- | --- | --- |
| Decks and Posts Installer Team A | 10 | 12 | Decks and Posts DP1- 24” stepped platform | Torpedo Levels (4), 3/8” Ratchet with 9/16 sockets (2), 3/8” Ratchet with 3/4 sockets (2), 3/8” Ratchet with “red” bit (2), 3/8” Ratchet with “blue” bits (2), 3/8” Ratchet with “star” bits (2), Allen Keys (3 blue, 3 brown, 5 red, 3 yellow, 3 orange), 25’ Tape measure (2), 9/16” open-ended wrench (2), 3/4” open-ended wrench (2), playground specs, |  | Robot |
| Team B | 10 | 12 | Playground components B1- Adventure Bridge B2 – Swings B3- Access gate (x3) B4- RockBlocks + Deck access support | 3/8” Ratchets with 9/16” sockets (1), 9/16” open-ended wrench (2), ¾” open-ended wrench (1), Allen keys (2 yellow, 2 orange, 2 brown, 2 blue, 5 red), 3’ tape measure (1), utility knife (1) sharpie, ½ deep socket |  | Foot print |
| Team C | 10 | 12 | Playground components C1- Sidewalk C2- Stationary Buttons ( 3-12” + 1-18”) C3- Inclined Cliff Hanger C4- 16” Stump C5- Hopscotch Climber C6- Crater Arch | 3/8” Ratchets with 9/16” sockets (1), 9/16” open-ended wrench (2), ¾” open-ended wrench (1), Allen keys (2 yellow, 2 orange, 2 brown, 2 blue, 5 red), 3’ tape measure (1), utility knife (1) sharpie |  | Hello Kitty |
| Team D | 10 | 12 | Playground components D1-Transfer Station + Approach Step D2- Stump Jump D3- Skylink D4- Ribbon Climber D5- Sliding pole | 3/8” Ratchets with 9/16” sockets (1), 9/16” open-ended wrench (2), ¾” open-ended wrench (1), Allen keys (2 yellow, 2 orange, 2 brown, 2 blue, 5 red), 3’ tape measure (1), utility knife (1) sharpie |  | Leaves |
| Team E | 10 | 12 | Playground components E1- Spiral Slide E2- Vertical Wave E3- Storefront panel E4- Drum Panel E5- Glide Slide | 3/8” Ratchets with 9/16” sockets (1), 9/16” open-ended wrench (2), ¾” open-ended wrench (1), Allen keys (2 yellow, 2 orange, 2 brown, 2 blue, 5 red), 3’ tape measure (1), utility knife (1)sharpie |  | Turtle |
| Team F | 60 | 70 | Mulch 190 Cubic Yards | Blue tarps, felt rolls, scissors, spray paint, duct tape, mats, 2D of playground | 2: | Happy Face |
| Team G | 12 | 15 | Concrete | Playground layout: marked buckets, nozzle, marking spray |  | All Star |
|  |  |  |  | PREP FOR SIDE PROJECTS |  |  |
| Team H | 15 | 18 | Painting: 1- Blue fence surrounding structure 2- Benches 3- Concrete border where it rises up to field 4- Base of tennis court wood | Sand, prime where necessary |  | Crayon |
| Team I | 0 | 10 | Painting Plywood Cutouts | Cut cutouts, prime, drill holes store- can be kids or follow- up |  | Ice Cream Cone |
| Team J | 7 | 10 | 7 deck benches | Cut wood, bundle, store |  | Sponge Bob |
| Team K | 10 | 15 | Moving DG/Planting 3 trees | Receive DG delivery, |  | Airplane |
| Team L | 10 | 15 | Demonstrative Garden | Map out plant layout |  | Heart |
| Team M | 12 | 14 | All other Planting (against gym, medians etc.) | Map out plant layouts |  | Butterfly |
| Team O | 0 | 10 | Garden Signs | Prime wood, finalize list- Can be kids or follow up |  | Candy corn |
| Team R | 2 | 3 | Green Team |  |  | Alligator |
| Total | 178 | 240 |  |  |  |  |
| Safety |  | 4 | Build Day Safety | Table, tent, first aid kit, sun block, gloves, masks, goggles, trash bags |  |  |
| Food |  |  | Build Day Food | Food, ice, utensils, drinks, coolers, paper products, trash bags |  |  |
| Youth Activities |  | 8+ | Youth Activities |  |  |  |
| Registration |  | 6 | Register volunteers | clipboards, volunteer waivers, nametags, pens, markers, balloons, helium, banners |  |  |