Draft Fundraising  Plan for SW Library Playground

The Fundraising Committee  Goal  - $120,000 to be raised by August 2011 includes in-kind donations.

Build day should be  September 23, 2011 or Oct 1, 2011.

Fundraising Methods

Events  $30,000

Community Businesses:  $12,000

Developer s:  $25,000 (plus in kind equipment and materials)

Foundations:  $10,000

Individuals:   $14,000

In-Kind:  $20,000

Suggested Recognition Categories  for Donors

Supporter  $200 to $900

Sponsor   $1000 to $2900

Patron     $3000 and upward

Children’s Hero  $10,000 and upward

Building Committee  will need to determine how and where to put names.  Ideas include Bricks with names, Fence Posts, and Plaques.

Organizing the Fundraising :  We ask for an overall planning and organizational meeting be called for early  January.   Felicia could then get folks to sign up for various activities.  We will need ten or more volunteers for the Fundraising Committee.

EVENT FUNDRAISING

Start Immediately with Kick-Off Caroling.

When:  Sunday December 19, 2010.  6 to 8 pm.

Fundraising Goal:  $2000.

What:  Christmas Caroling Fundraiser

Details:  With help from church leaders and parents  and social networks, we will identify lead “block” organizers who will host caroling parties for their area.  Hosts will serve hot cider and cocoa, etc.  Organizers  (Eve and Melissa)will prepare  carol words; fundraising letter to leave with homes; a basket for collection and general instructions .  Goal is to have following areas covered:

2 groups G Street, SW ( from 7th to 4th and  from 4th to South Capitol.)  Possible organizers, Bridget, Anne, or Abigail Sloan ; and  the Fouts.

I Street, from 7th  through 3rd---

N Street, SW

Carrollsberg

River Park

Tiber Island

The remainder are ideas only

When:   January- Skating Party at Memorial Art Gallery . Block of tickets will be purchased in advance. Cocoa, and cookies, etc. will be brought by group.

Alternative:  Kids Jazz Concert at Westminster

When:  February. Valentines drinks and dinner at Channel Inn

When:  March  Community Rummage and Plant Sale

When:  April Cherry Blossom Festival Food Booth and Tee Shirt sales??

When:  May Kids Fair

When:  June National Game Tickets --- or donated boxes (raffle or purchase of bulk at reduced rate, and re-sale at added cost?)

When:  July---

When: August

Apartment and Townhouse Management Groups: $500 to $1000 will be sought from each development, depending on size.  If they are prohibited from contributing, we will ask to be permitted to go door- to- door in building.

Developer Fundraising -  $25,000 cash and in-kind materials and equipment, such as leveling for ground.  Small sub-committee will approach Hoffman; Rodells; Lerners, etc.

Business Fundraising-  $12,000. The many businesses operating in the community will be approached through letter and visit.  Some in-kind will be sought, such as food for the Build Day.  However, most will be asked for $500 to $1000 contributions depending upon size of organization. ( A group of 5 volunteers will be sought to  reach the businesses.)