## Sheet1
Virtual Desktop Infrastructure (VDI) Implementation Plan
Task | Start Date | Finish Date
Planning services
Evaluate how many desktops to virtualize
Evaluate the number of thin clients to be used
Evaluate how many VDI hosts to be implemented (based on the number of desktops)
Evaluate Server Resource Allocation Needs
Capital approval process for one server, one thin client to build test environment
Order approved test equipment
Price additional servers, thin clients, SAN storage requirements
Proof of Concept
Build proof of concept environment to later be moved into production
Install virtualization software on server
Build desktop virtual machine
Configure thin client device to connect to virtual desktop
Backup solution to ensure VDI is recoverable
Test Phase
Sysprep virtual desktop to create a deployable template
Test deploying template
Test connectivity to VDI from the VPN
Test usage of thin client and virtual desktop
1st Quarter Implementation Phase
Deploy 5 virtual desktops to replace 5 physical desktops
Training to end users
Monitor and Support
Maintenance schedule for VDI hosts
2nd Quarter Implementation Phase
Order additional equipment (servers, thin clients, software licensing)
Deploy additional servers to support remainder of the project
Deployment of virtual desktops to each department
Training to end users
3rd Quarter Implementation Phase
Order additional equipment (servers, thin clients, software licensing)
Deploy additional servers to support remainder of the project
Deployment of virtual desktops to each department
Training to end users
4th Quarter Implementation Phase
Order additional equipment (servers, thin clients, software licensing)
Deploy additional servers to support remainder of the project
Deployment of virtual desktops to each department
Training to end users
NEED TO ADDRESS SECURITY IN THIS PLAN…