






Robert J. Kapsch







January 9, 2005

Paw Paw Tunnel Chronology

Chesapeake and Ohio Canal
1835 – Morris suggests “Devil’s Eyebrow” region across from Doe Gully, WV as possible location of a canal tunnel.

1835, End of – Attention shifted to Paw Paw Bends as location for tunnel.

1835, November 16 – Morris submits recommendation and cost estimate to Fisk for Paw Paw Tunnel.

1835, December 19 – Fisk submits letter recommending a double tunnel at Paw Paw Bends to C & O Canal President and Directors.

1835, December 21 -  Fisk’s report considered by President and Board of Directors.  Without much debate the Board approves construction of tunnel and preparation of detailed plans.

1836, February 10 – Fisk submits plan and specifications and Board approves them.

1836, February 17 – Board solicits proposals from prospective contractors.

1836, March 15 – Board considers some proposals submitted for tunnel and “deep cuts.”
 

1836, April 6 – Board approves contract with Lee Montgomery
 – had constructed a tunnel on the Dansville and Pottsville Railroad.
  Date of completion was set for July 1, 1838.

1836, June – Montgomery begins work on Paw Paw Tunnel.

1836, December 1 – Morris submits plan on contract for tunnel to Fisk.

1836, December 28 – Montgomery submits letter to Fisk on problems getting skilled labor for tunnel.

1837, August 26 – Montgomery reports he has 250 men working on tunnel and related construction.
 Work was averaging ten to twelve feet per week (compared to seven to eight feet a day by a single hand earlier reported by the Board).  Montgomery was having financial problems.
1837, August 30 – Board advances Montgomery $2,500 – not enough to substantially help him.

1838, February 15 – Morris writes Fisk that Montgomery stands “upon the brink of insolvency.”

1838, February 21 – Morris writes Fisk, “I am receiving notice of riotous movements…”

1838, February 18 – Morris writes Fisk that riots may occur due to non-payment of the 400 workers at Paw Paw Tunnel.

1838, April 11 – Board approved $1.40/cu. yard for rock excavated but nothing additional for earth excavation and an advance of $25,000.  Trouble was temporarily avoided.

1838, early – Riots broke out.

1838, May 1 – 529 linear feet of tunnel driven, of 3,118 feet total.

1838, May 8 – General Ortho Williams receives letter from Charles Fisk, C & O Canal, that 180 unemployed canal workers are at Prather’s Neck, they had been there for three weeks, that threats have been made to injure Company property and that Fisk thought that difficulties would arise in the next couple of days, perhaps tomorrow.
 General Ortho H. Williams replies that he could not order out troops unless required to do so by three Justices of Peace.

1838, May – General strike along most of construction line.  Militia responded and seized 140 kegs of powder.

1838, June 14 – General Ortho H. Williams receives requisition from three Justices of the Peace to order out troops.

1838, June 15 – Colonel Fitzhugh, on orders of General Ortho H. Williams, proceeds to Clear Spring, near “Prathers Neck,” but his officers couldn’t induce the men (volunteer militia) to muster and that gave encouragement to the rioters.

1838, June 16 – General Ortho Williams successful in sending 40 troops (out of original 160) from Hagerstown which was joined by a small force from Colonel Wolf’s Regiment and Capt. Barnes’ Calvary.  They met little or no opposition, arrested only one man and took control of 140 kegs of powder.

1838, June 21 – Plan of a Railway for Athey’s Hollow – see 5 x 8 cards.
1838, Latter part of June – Rioting broke out at the tunnel and contractor was authorized to discharge all hands and suspend construction.
  
1838, August 1 – Action taken to discharge 130 workers and “black-list” them, most from the tunnel.

1838, November 28 – Ellwood Morris to reports to Chief Engineer Charles Fisk the number of men killed and wounded due to accidents with the hoisting machinery at Shafts B & D:



Killed & Wounded



Shaft B
2 killed  2 wounded



Shaft D
4 killed  0 wounded
He adds, “The 3 men killed yesterday were in shaft D.”

1839, June – Status – 1,984 feet of tunnel has been driven – 1,134 feet remain.  Total length is 3,118 feet.

1839, August 11 – Sunday morning, early.  Irish workers attach “Dutch” worker while they are asleep and drive them off.  Fourteen men wounded, some severely.  Workers made escape by swimming the river.  One man shot at while in river.  Only one instance of the violence.

1839, August 15 – Two Allegany County justices of the peace demanded General Ortho H. Williams order out the troops to quiet the “insurrection.”

1839, August 18 – Governor William Grason authorizes General Ortho H. Williams to muster the militia.

1839, August 22 – Colonel Thurston sends George W. Haller and G.W. Reid to obtain information about the riot desired by General Ortho H. Williams.

1839, August 27 – Colonel Thurston marches with 150 men (from Cumberland).
  “Two riotous and unlicensed houses were destroyed,” 40 or 50 shanties and shops destroyed (as identified by Fisk), 120 weapons captured and destroyed, 26 arrested (one was killed, accidentally).

1839, October – Ellwood Morris advertises for a contractor to make bricks.

1839, November 21 –Ellwood Morris advertises for a contractor to provide 1 million bricks to be delivered at south portal, Paw Paw Tunnel.

1840, May – Only 94 linear feet of tunnel to be driven.
  
1840, June 3 – Heading were driven through to a junction.

1841, April 13 – Ellwood Morris resigns.

1842, beginning – Montgomery economic situation was hopeless.

1842, end of – All work came to an end.

� Letter, Morris to Fisk, Aug. 1 and 3, 1835, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 3, footnote 5.


� Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 3.


� Letter, Morris to Fisk, November 16, 1835, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), pages 3-4, footnote 7.


� Letter, Fisk to President and Directors, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), pages 4-5, footnote 8.


�  Proceedings, President and Directors, December 21, 1835, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), pages 6, and footnote 7.


� Proceedings, President and Directors, February 10, 1836, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 6, and footnote 10.


� Proceedings, President and Directors, February 17, 1836, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 6, and footnote 11.


� Proceedings, President and Directors, March 15 and 30, 1836, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 7, and footnote 12.


� Proceedings, President and Directors, April 6, 1836, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 7, and footnote 12.


� Letter, Morris to Fisk, November 16, 1835, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 7, and footnote 13  -- but no information is contained in footnote 13.


� Letter, Montgomery to George Bender, August 26, 1837, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 10, and footnote 18.


� Letter, Morris to Fisk, Plans for Contract for Tunnel at Paw Paw Bends, December 1, 1836, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 9, and footnote 15.  


� Letter, Montgomery to Fisk, December 28, 1836, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 11, and footnote 20.





� Letter, Montgomery to George Bender, August 26, 1837, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 16-18, and footnote 27.


� Proceedings, President and Directors, August 30, 1837, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 18-19, and footnote 28.


� Letter, Morris to Fisk, February 13 (sic – in text Luzader states it was February 15) 1837 (sic – the sequence suggests 1838, not 1837), as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 19-20, and footnote 30.


� Letter, Ellwood Morris to Charles Fisk, February 21, 1838, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 22, and footnote 33.


� Copy in Letter, Morris to Fisk, February 21, 1838, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 22-23, and footnote 33.


� Proceedings, President and Directors, April 11, 1838, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 26-27, and footnote 36.


� As stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 28, and footnote 40.


� Chesapeake and Ohio Canal Company, Eleventh Annual Report (1839), page 10.


� Letter, General Ortho H. Williams to Governor Thomas W. Veazey, June 4, 1838, as included in State of Maryland, Executive Communication. In reply to an order of the House of Delegates, of the 3d of January, 1839, Relative to a Draught of the Militia, in Washington and Allegany Counties, January 4, 1839, page 2.


� Letter, General Ortho H. Williams to Governor Thomas W. Veazey, June 4, 1838, as included in State of Maryland, Executive Communication. In reply to an order of the House of Delegates, of the 3d of January, 1839, Relative to a Draught of the Militia, in Washington and Allegany Counties, January 4, 1839, page 2.


� Letter, General Otho H. Williams to Washington, May 17 and 18, 1838, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 29, and footnote 44.


�  Letter, General Ortho H. Williams to Governor Thomas W. Veazey, June 4, 1838, as included in State of Maryland, Executive Communication. In reply to an order of the House of Delegates, of the 3d of January, 1839, Relative to a Draught of the Militia, in Washington and Allegany Counties, January 4, 1839, page 2.


�  Letter, General Ortho H. Williams to Governor Thomas W. Veazey, June 4, 1838, as included in State of Maryland, Executive Communication. In reply to an order of the House of Delegates, of the 3d of January, 1839, Relative to a Draught of the Militia, in Washington and Allegany Counties, January 4, 1839, page 2.


� Letter, General Ortho H. Williams to Governor Thomas W. Veazey, June 4, 1838, as included in State of Maryland, Executive Communication. In reply to an order of the House of Delegates, of the 3d of January, 1839, Relative to a Draught of the Militia, in Washington and Allegany Counties, January 4, 1839, page 2.





� Proceedings, President and Directors, June 28, 1838, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 30, and footnote 47.


� Proceedings of the President and Directors, July 12, 1838 and Notice to Contractor, signed by Fisk, August 1, 1838, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 30, and footnote 48.


� Letter, Ellwood Morris to Charles B. Fisk, November 28, 1838, National Archives, Record Group 79, Entry 214.


� Chesapeake and Ohio Canal Company, Eleventh Annual Report (1839), page 10.


� Letter, Ellwood Morris (?) Asst. Engr. To Charles B. Fisk, August 12, 1839, National Archives, Record Group 79, Entry 207.


� Baird, David, “Violence Along the Chesapeake and Ohio Canal: 1839,” Maryland Historical Magazine, Volume LXVI (1971), pages 121-134, page 124.


� Baird, David, “Violence Along the Chesapeake and Ohio Canal: 1839,” Maryland Historical Magazine, Volume LXVI (1971), pages 121-134, page 125.


� Baird, David, “Violence Along the Chesapeake and Ohio Canal: 1839,” Maryland Historical Magazine, Volume LXVI (1971), pages 121-134, page 125.


� Baird, David, “Violence Along the Chesapeake and Ohio Canal: 1839,” Maryland Historical Magazine, Volume LXVI (1971), pages 121-134, page 127.


� Baird, David, “Violence Along the Chesapeake and Ohio Canal: 1839,” Maryland Historical Magazine, Volume LXVI (1971), pages 121-134, pages 128-9.


� Advertisement, Ellwood Morris, October 1839, National Archives, Record Group 79, Entry 214


� Advertisement, Ellwood Morris, November 21, 1839, National Archives, Record Group 79, Entry 214.


� Chesapeake and Ohio Canal Company, Fisk Report in Twelfth Annual Report (1840), page 15.


� Progress of Work, Tunnel Residency, May, 1840, as stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 39, and footnote 67.


� As stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 40.


� As stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 43.


� As stated in Luzader, John F., Historic Structure Report, Paw Paw Tunnel, Chesapeake and Ohio Canal, Part I, Administrative Section, Typescript, (Washington, D.C.: National Park Service, Chesapeake and Ohio Canal, n.d. ca. 1965?), page 46.





PAGE  
7

