## Work Breakdown Structure
Toy Launch Event
Plan, Planning and Preparation | Dinner/ Goods | Advertising and Guests | Event Execution
1.1 Define event goals and objectives | 2.1 Rent event space and secure necessary permits | 3.1 Develop marketing and promotional materials (invitations, flyers, posters, etc.) | 4.1 Set up event space and arrange equipment
1.2 Determine event date, time and location | 2.2 Hire event planner (if necessary) | 3.2 Promote the event through social media, email, and other channels | 4.2 Welcome and register attendees
1.3 Define event budget | 2.3 Book catering, audiovisual equipment, and entertainment | 3.3 Collaborate with media outlets | 4.3 Coordinate with catering for food and
1.4 Conduct market research to target audience | 2.4 Arrange transportation and parking for attendees | for coverage | beverage service
1.5 Select event theme and color scheme | 2.5 Coordinate with speakers for presentation materials |  | 4.4 Oversee audiovisual equipment
and presentations
4.5 Manage event staff (registration, coat check, etc.)
Toy Launch Event
t

## Brainstorming Timeline
Even 1 tart Project Initiation (Jan 3th) Define project scope and goals (Jan 4th) Gather project requirements (Jan 5th - Jan6th) Assign roles and responsibilities (Jan 7th) Schedule project kick-off meeting (Jan 13th) Finalize project budget (Jan 14th) | Event 2 Project Kick-Off Meeting (Jan 15th) Start Design and Planning (Jab 16th) Finalize project schedule (Jan 17th) Create project deliverables list (Jan 18th) Assign tasks to team members (Jan 19th) Start development (Jan 20th) Set up project management tools (Jan 21st)
Jan 3, 2023 Jan 15, 2023
Jan 22, 2023 Jan 28, 2023 Feb 7, 2023
Even 3 Review progress and adjust project schedule (Jan 22nd) Continue development (Jan 23rd - Feb 28th) | Perform quality assurance testing ( 1st - Feb 3rd) Resolve any identified issues (Feb 4th - Feb 7th) | Conduct user acceptance testing (Feb 8th - Mar 10th) Prepare for project closeout (Feb 11th) Conduct project closeout meeting (Feb 12th) Submit final project deliverables (Feb 13th) Close project (Feb 14th)

## Gantt Chart
JANUARY FEBRUARY MARCH
PROJECT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PHASE ONE |  |  |  | PROJECT CHARTER |  |  |  | Review progress and adjust project schedule (Jan 22nd) Continue development (Jan 23rd - Feb 28th)
PROJECT MISSION | Party Planning Corporation, |  |  |  | PLAN REVIEW
which is a company Toy launch event
PHASE TWO
PROJECT PLANNING |  | tart Project Initiation (Jan 3th) Define project scope and goals (Jan 4th) Gather project requirements (Jan 5th - Jan6th) Assign roles and responsibilities (Jan 7th) Schedule project kick-off meeting (Jan 13th) Finalize project budget (Jan 14th)
Project Kick-Off Meeting (Jan 15th) Start Design and Planning (Jab 16th) Finalize project schedule (Jan 17th) Create project deliverables list (Jan 18th) Assign tasks to team members (Jan 19th) Start development (Jan 20th) Set up project management tools (Jan 21st)
Work Bkdwn
Contt Chart
Communication Plan
Bck Mangement
status and Tracking
KPC
Questy
PHASE THREE
Status and Tracking
PROJECT | KPC
Qualty
Forecasts
Conduct user acceptance testing (Feb 8th - Mar 10th) Prepare for project closeout (Feb 11th) Conduct project closeout meeting (Feb 12th) Submit final project deliverables (Feb 13th) Close project (Feb 14th)

## Expenses”
TOY EVENT LAUNCH PLANNING
SITE | ESTIMATED | ACTUAL
ROOM AND HALL FEES SITE STAFF EQUIPMENT TABLES AND CHAIRS
| 1500 | 500
| 3000 | 1200
| 5500 | 5800
| 4000 | 3000
TOTAL | 14000 | 10500
DECORATIONS | ESTIMATED | ACTUAL
BALLOON PAPER CUPPLIEE FLOWERE CANDLEE LIGHTING
| 850 | 300
| 750 | 550
| 800 | 600
| 700 | 400
| 1700 | 800
TOTAL | 5450 | 2650
PUBLICITY | ESTIMATED | ACTUAL
Work with graphics, photocopying, printing, postage
| 300 | 700
| 4000 | 5500
| 1000 | 2500
| 300 | 200
TOTAL | 5600 | 8900
MISCELLANEOUS | ESTIMATED | ACTUAL
FOX SERVICE PROVIDED BY TELEPHONE TRANSPORTATION STATIONERY
| 300 | 650
| 600 | 550
| 1400 | 1300
| 200 | 250
TOTAL | 2500 | 1750
REFRESHMENTS | ESTIMATED | ACTUAL
FOOD DRINKS LINENS STAFF AND GRATUTIES | 2000 | 1800
| 500 | 450
| 400 | 300
| 16000 | 12000
TOTAL | 18500 | 14550