Portfolio Project

Jerett Schicker

Bryant & Stratton College

BUSS215: Management Principles

Sheryl Hertel

April 24th, 2021

Introduction

My name is Jerett Schicker, and this is my proposal submission to organize a fundraiser for the West Allis High School baseball team, The West Allis Alligators. This proposal will go into detail about all aspects of managing this project including planning, organizing, staffing, controlling, and leading. It is my hope that the success of this event will lead to the formation of a non-profit organization of West Allis School District parents and small businesses that helps fundraise for our children’s school events.

Planning

The objective of this event is to raise at least $1,600 towards the purchase of baseball uniforms for the West Allis High School baseball team, the West Allis Alligators, by generating revenue from the sale of food, beverages, fair games, a car wash, and donations. The expenses generated from planning and organizing this event will be repaid through additional revenues generated by the event as well as all expenses for the planning and execution of the event. Any revenues in addition to the cost of operational expenses and price of team uniforms will be allocated for future use by the team such as transportation, travel lodging, merchandise, and other miscellaneous expenses. To achieve this objective, the following action plan and priorities listed will need to be fulfilled and accomplished.

Many local businesses have offered to help us with this event by donating some of their goods, services, and time. The fire department has allowed us to use their picnic grove near the fire station to hold the event. We will also have four volunteers from the fire department to help us with parking for the event as well as run a car wash in front of the fire station. The Pick-N-Save grocery store across the street from fire station has graciously donated cleaning supplies for the Firefighter’s Carwash, as well as burgers, hot dogs, buns, and soda for us to sell. Pick-N-Save is also reserving a portion of their parking lot for volunteers and attendees to park. The Garage Gastropub on Greenfield Avenue is donating a bartender and cook for the evening. Even though no alcohol will be served at this event, the bartender will serve sodas and other non-alcoholic beverages to attendees. The cook will be operating the firehouse’s grill to cook the burgers and hot dogs to sell. The Garage Gastropub is also donating a variety of their best appetizers for attendees to purchase. I will need two more volunteers to help serve the appetizers and food as well as take payments from guests. Home Depot has donated some supplies and allowed us to waive the rental fees on some equipment to build some fair games for attendees to play during the event. They are also letting us use some of their outdoor event tents to set up booths and vender spaces for the event. We will be building our own bag-toss boards, sewing bean bags, and painting the boards. We will also need someone to paint glass bottles and wooden rings for a ring-toss game. I will need 4 volunteers to help build, sew, paint and then operate the fair games during the event. The Toy Chest, a local toy store, will be selling us some stuffed animals and other toys, at cost, for use as prizes for the games. I will need 3 more volunteers to help me chaperone the baseball team as they canvas the town with flyers to promote the event. These 3 volunteers will also help me on the day of the event to oversee ticket sales and help me manage the event itself. I will be collecting all of the supplies, food, and drinks from donating businesses and will coordinate teams to help prepare and run the event. There will also be a spot for 3 local businesses to sell their products at this event. Lastly, the local theater house is letting us use their outdoor stage for the event. Three local bands will perform over the course of the day, providing use with live music for the whole event.

For the location, the total area used will be the front of the fire station, the fire station’s picnic grove, a portion of Pick-N-Save’s parking lot, and the alleyway near the back of the picnic grove will be closed off and used as the stage area for the bands to perform. Street parking on the street between Pick-N-Save and the fire station will also be reserved for event attendees. The firefighters will have their car wash in front of the fire station. The entrance to the picnic grove will have a ticket booth and 3 vendor booths. Next will be a seating area and tent for the grilling area and non-alcoholic beverage bar using the existing picnic tables. A few standing tables will be rented for the event for attendees to use as well. Next, in the open space in the middle of the grove we will have the fair games area set up. We will also be renting a dunk tank and hiring a clown from MacDonald’s Petting Zoo and Farm to be set up in this area. Near the back of the open space will be an area for attendees to mingle and dance as they listen to live music from the bands playing on the stage in the closed-off alleyway at the back end of the picnic grove. Lastly, there will be a reserved area of the Pick-N-Save parking lot for attendees and volunteers to park.

The main promotion for the event will be through the baseball team itself canvasing the business district as well as the area surrounding the fire station with promotional flyers. Flyers will be put up in businesses around the community, handed out to individuals, and put on cars in the parking lots of business that allow it. Three chaperones will assist and look over the team as they hand out flyers. Pick-N-Save will have a large poster put by their customer service desk where they will sell discounted tickets for the fair games to help promote the event. We will also run ads in two local radio stations for 2 weeks leading up to the event. Lastly, students at West Allis High School will be given flyers to give to their parents with one free ticket to the fair games included.

The main source of revenue for this event will come from food and drink sales as well as from tickets to play the fair games. Once expenses are paid, the rest of these proceeds will go directly to the baseball team. The firefighters will also be donating 100% of the revenue from their carwash to the team. We will also have donation bins near the entrance, food, and stage for attendees to donate directly to the baseball team. Lastly, we will also generate revenue by selling 3 vendor spaces for $100 each to 3 local businesses. We will not collect any percentage of their sales during the event, however.

Upon approval of this event proposal, I will send out an email to all donating businesses, and volunteers listing next steps. I will also coordinate an initial meeting with volunteers as well as schedule periodic meetings leading up to the event. At the initial meeting, I will ask for volunteers for each task, delegate when needed, and appoint team leaders for each project leading up to the event.

Organizing

Upon acceptance of this proposal, I, Jerett Schicker, will form a tax-exempt, nonprofit organization (501(c)(3)) as the founding member (Internal Revenue Service, n.d.). The nonprofit corporation will be called WAPASA (West Allis Parent’s Association for School Activities) and will be the main organization responsible for fundraising for extra-curricular activities for the West Allis School District (WASD). Once founded, I will request the help of the West Allis School Board to hold a meeting for parents with students in the WASD. In this meeting, we will nominate and elect members for the Board of Directors for WAPASA. As a founding member, I will start as a member of the Board of Directors as well as the Executive Director of WAPASA until the next election determined by the Bylaws (Internal Revenue Service, n.d.). The reason I am proposing the formation of a nonprofit organization is to create support for future fundraising events for the WASD. As a nonprofit WAPASA will have more resources available to create fundraising opportunities for our children and students. WAPASA will also be tax-exempt and donations to our nonprofit organization will be tax deductible (Internal Revenue Service, n.d.).

The following page has a diagram of the proposed organizational hierarchy for WAPASA. This will allow WAPASA to have a clear chain of command and divide the responsibilities of the organization, respectively.

I am proposing this hierarchal structure because it will allow WAPASA to grow as an organization overtime. In the initial stages of WAPASA not every position will need to be filled and individuals working for WAPASA may fill more than one position in the hierarchy. For example, I may initially double as both the executive director and program director. As WAPASA grows, we will need to hire to fill these positions as needed.

In this hierarchy, I will report directly to the board of directors as Executive Director. I chose to have an executive assistant because they will help me answer phone calls, direct messages, and schedule meetings. The executive assistant will also manage WAPASA’s main email account and social media accounts. They will interact with the WASD on my behalf and take messages from parents and member/volunteers.

The first director position is the Finance Director. They will manage the overall accounting for WAPASA as well as the fundraising program. The Finance Director will also oversee Accounts Payable and work directly with their Financial Assistant. They will also work closely with the Business Liaison Officer to seek funding and partnerships with local businesses. They will also work with the Board of Directors and Event Planning Coordinator to create a budget for events. The second director position is the Administrative Director who will oversee all the office functions to make sure everything is running efficiently. They will also be in charge of the hiring and training of WAPASA employees and volunteers. They will have a Member/Volunteer Coordinator that reports to them who assists in training and staffing both for the administrative offices and special events. They will work closely with the event planner to determine staffing needs. They will also help negotiate contracts with the WASD and local businesses, so they will work closely with the Business Liaison Officer as well.

For now, the third director position, the Program Director, will be filled by me. I will oversee the planning, organization, and implementation of both WAPASA’s organizational programs and special event programs for fundraising. I will work directly with my Event Planning Coordinator to plan, schedule, organize, staff, and execute special fundraising events for the WASD. I will also work directly with my Business Liaison Officer to secure donations and funding from local businesses for the events. I will work closely with the other directors to budget for these events and have the proper administrative functions and staffing needs in place. I will also work closely with the WASD to determine the need and scope of fundraising events each year.

Staffing

In order to plan, prepare, and staff the event, we will need 15 volunteers in total. These 15 volunteers will be split into four main groups – Parking and Carwash, Food and Beverage, Fair Games, and Chaperones/Event Staffing. These groups will be a mix of volunteers from donating businesses and organizations and volunteer parents of the West Allis Alligators Baseball Team.

The Fire Department will be providing four volunteers from their firehouse to operate the carwash and manage parking for the event. Three firefighters will be working for the carwash and one firefighter will oversee parking. The second group will be in charge of operating our food and beverage area and will have a total of four volunteers. Two volunteers, a cook and a bartender, will be from the Garage Gastropub. The cook will operate the Firehouse’s grill to cook burgers and hotdogs for the event, and the bartender will serve non-alcoholic beverages to guests. This group will also have two other parent volunteers, with one serving food and appetizers to our guests and one working as a cashier to handle the food and beverage sales.

The third group will be a group of parent volunteers that will create and operate the fair games area of the event. I will need two volunteers to help with the construction of the bag-toss boards and ring-toss platform. I will need one volunteer to help sew and create bean bags for the bag-toss game, and a fourth volunteer to help paint the bottles, rings, and boards for the games. During the night of the event, these same four volunteers will help operate the fair games, collect tickets, and hand out prizes. One of these volunteers will also assist the clown we have hired for the dunk tank. The fourth and last group will be comprised of three parent volunteers who will be chaperones for the baseball team as they pass out flyers to advertise for the event. These three volunteers will also double as event staffers on the day/night of the event. I will need one parent to staff the front entrance table and sell tickets to guests. The other two parents will help me make sure the event is running smoothly and assist with any issues that arise during the event.

The first meeting for the planning of this event will take place three months before the event. It will be an open Zoom meeting, where all baseball players’ parents will be invited to attend. The invite will also be sent out to the Garage Gastropub, the Firehouse, and the Pick-N-Save store manager. During this meeting, we will discuss the needs for organizing and staffing this event as well as ask for volunteers for the different teams. We will also elect team leaders for each of the teams. The team leaders will be in charge of coordinating communication among their team and fulfilling the objectives for each team. I will meet with the team leaders once a week over Zoom to pass along any further information, check-in on their progress, and answer any questions, etc. The morning of the event, all teams will meet in person at the Firehouse to discuss any further steps that need to be taken, projects that need to be completed, and begin setting up for the event.

Controlling

For this event, the system of internal controls we use will be fairly simple. We will be giving each volunteer a simplified set of policies, or code of conduct, for them to sign. We will also have a liability waiver for them to sign as well. For inventory, I will be keeping track of donations, including food, beverages, and other supplies prior to the event by the use of an internal audit, or inventory. I will have a volunteer sign off on inventory with me the day of the event as well to make sure I am also being held accountable. Revenue will be managed the same way, and the volunteers in charge of handling money on the day of the event will also be held accountable through an internal audit to make sure the revenue (cash) at the end of the event matches the sales we made.

Once a team is assembled for WAPASA, the non-profit organization I am starting to help fund our children’s school events, we will handle internal controls more systematically. We will develop and update a full-fledged package of policies, procedures, and ethics code for our employees to sign. As executive director, I will be working closely with my assistant and Administrative Director to develop and implement these guidelines. The administrative director will also develop a set of objectives and standards to use when completing performance appraisals for our staff. We will use a performance evaluation-reward system to administer bonuses, pay raises, etc.

At WAPASA, each department (Finance, Administration, and Program/Event Management) will oversee their own physical inventories, including anything that has been donated. They will report the result of their physical inventories to the Finance director at the end of each quarter to make sure that the inventory results match the accounting for the same period. As for revenue, the Finance Director and his/her team will be in charge of handling the revenues and accounts for each department and subdepartment. We will utilize GAAP practices to manage our accounting system and provide a transparent control over our organization’s finances.

Leading

I hope to use the success of this event to show that I am a capable leader that will be able to build WAPASA into a strong organization that helps provide funding for our children’s school events. As parent’s we are often the servant leaders that help our children grow into future leaders themselves, and I believe that access to school events is a key step to facilitate this growth. In the 1970’s Robert Greenleaf first used the term “servant leadership” to describe a leader whose main purpose is to serve those he/she is leading (Greenleaf, 2007). I see myself as a servant leader, both through serving the organization and staff itself, and through our organization’s work of serving the community. I hope that by showing the benefits a servant leader can bring to a community, I will draw other parents and community members in to help serve the community they live in as well.

Conclusion

As you can see, this proposal highlights the details and the amount of research and planning that has been completed in order to create this fundraising event and eventual non-profit organization. As the planning coordinator for this event, I have all of the donations from local businesses and volunteers from the community planned and ready to work. My organization of this event also extends beyond the event itself by creating a non-profit organization, the West Allis Parent’s Association for School Activities (WAPASA), that will help provide funding for many other school events for students in the West Allis School District. I have also included information for how the event itself will be staffed as well as the organizational structure of WAPASA and each position’s job duties. Lastly, I have shown how I plan to utilize the controlling and leading functions of management to monitor and direct both the event and WAPASA as an organization. I will use meetings and performance evaluations to control staff, conduct internal audits of our inventory, and use accounting practices to monitor revenues and donations. In leading this nonprofit organization, WAPASA, and managing a successful fundraising event for the West Allis Alligators, I hope to showcase my leadership role as a servant leader of this community. As a community of parents and teachers, we are all servants tasked with the goal of raising and teaching our children to become future leaders. I believe that extracurricular activities such as sports and the arts play a crucial role in this development of our kids, and I hope that you can entrust me and WAPASA to be a part of this goal.

# References

Greenleaf, R. K. (2007). The Servant as Leader. Corporate Ethics and Corporate Governance, 79-85.

Internal Revenue Service. (n.d.). Charities and Nonprofits. Retrieved from IRS.gov: https://www.irs.gov/charities-and-nonprofits