Portfolio Project

LaWanda Webb

Bryant & Stratton College

BUSS215: Management Principles

Instructor Gaiser

December 15, 2021

Introduction

I’m writing a proposed solution to obtain new sports uniforms at my child’s school. “When you look good, you feel good” is the truth.  With the resources at hand, I will love to involve the community and raise the funds. I propose a school fundraiser to collect the funds needed for uniforms. New uniforms will not only look good, but it could teach the children the importance of teamwork and working together to accomplish a goal.

Planning

A school fundraiser will allow the community to come together and do something amazing for the school district. The cost of these new uniforms is $1600.00, and I came up with a way to raise the funds in a timely fashion. Community Day Auction will not only allow us to raise money by charging a cover fee, selling food, and different items, but allow members of the community to intermingle and become familiar with the local vendors. A communication schedule along with donor tracking plans and a detailed breakdown of want every volunteer does and when. In order for us to reach our fundraising goal, we have a few incentives in place such as direct recognition and some fundraising merchandise.

As the organizer of this project, I’m have obtained the assistance of 15 volunteers to help with figuring out costs and promotion, a location as well as many local businesses such as restaurants, bars, stores and etc. have agreed to donate certain goods and services to the event. The local fire department has offered its picnic grove for free as the use of location for the auction.

As the location of the fundraiser is pretty big, we have also designated spots for the local vendors to sell and promote their goods as well. I will form groups of volunteers to promote as well as have specific jobs to ensure this fundraiser is a success. This fundraiser is a great way to promote the community, collaborate, and improve the school uniforms. This written plan will allow us to focus what we want and create a process to get it.

Organizing

A functional organizational structure will be used in order to help us facilitate a smooth fundraising event in which all volunteers will report to me as the lead organizer of this Community Day Auction. It’s extremely important for this fundraising event to be properly organized, however, from managing my team of volunteers, advertising, and setting the objective.

Every detail has to planned accordingly and splitting up the responsibilities is ideal. Regular meetings and communication will ensure it’s no kinks and everyone is familiar with their role. I believe this is the best structure for my team since several of these volunteers have participated one way or another in previous fundraising. The organizational structure will focus on a team approach but will have functional structure as well to ensure the event is organized.

The leader who is well organized, focus, and the most knowledgeable of fundraising, will report directly to me as the organizer to prevent confusion. I selected Joann/lead to be the one to report directly to me because she has tons of experience organizing several successful fundraisers, member of PTA, and respected pillar in the community. Joann responsibilities include contacting potential donors, storing donors’ information, and keeping track of the donations. As a leader, they will interact with donors, local vendors, and community members who has interest in the auction whether it’s by social media, email or face-to-face, informing them how they can support, how the funds will be used, and just connecting/building with them. We are looking to make this event as successful as possible to uplift the children.

Staffing

I have 15 volunteers on board with my idea to accomplish this fundraiser. Adequate staffing, support, and structure are needed to have a successful event, therefor five teams will be put in place. One team consisting of maybe 3 or 4 volunteers will assist me in hanging flyers around the neighborhood in local shops, school website, spreading the word to family and friends, and promoting the event through social media such as Facebook and Instagram to spread the word in the best ways and reach a wider audience.

A team of volunteers is important because no fundraiser is organized on its own, it will be a fun experience, and possibly we can raise more. By designating teams to help with this fundraiser, we will have everything covered by people who already support the cost. The other teams will help out with donors, donations, food, budget, and items to be auctioned to make sure everything work together.

Communication will occur often at least once a week between all members involved whether its via phone, zoom, and meetings held face-to-face to answer all questions and concerns.  That way, it ensures word gets out and it builds relationships among the volunteer/staff of the event. Frequent communication is a must to stay on track of things regarding this auction between the volunteers, myself, and the fire department. The volunteers and I will agree on mutually acceptable and realistic expectations of this fundraiser. “Essential to any strong relationship is trust”. (Cahalane, 2017) Fundraising isn’t easy, it takes a lot of work, so I as the organizer of this event I want all the volunteers to share in sharing this mission of giving back.

Controlling

To help control and stay sane, the fundraising event needs to be as stress free as possible. Setting up a calendar as reminder for important deadlines is critical, however, it also provides a way of staying organized and coordinating between different areas. To control the aspects of this, fundraise most of the volunteers will have specific tasks such as planning the parking, collecting donations, assisting local vendors, or getting last minute supplies, I personally will deal with anything that comes up unexpected. I find it better to have many helping hands versus not having enough.

Inventory will collect and managed by a team of 4 volunteers, Joann who is leading the volunteers will collect, track, and document every donation whether it’s from a local business, community members, auction sales, or outside vendors. Online donations which give people a convenient way to show the generosity will also be accepted. Receipts will be provided for written records of every donation received from a donor.

The plan to collect the revenue will be through ticket sales, raffles, and 40% of the proceeds collected at the silent auction during Community Day will go towards purchasing new uniforms. We will be keeping record of how many tickets are sold and how many each volunteer sells. This way I, as the organizer can predict the expected revenue made. A donation box will be available on the grounds as well as I will have two volunteers to collect, manage, and protect all monetary donations. Once all revenue is collected, the funds will be transferred to the hands of the school committee to purchase the new uniforms.

Leading

Managing a fundraising is no easy task, but with adequate planning and research, it can be successful. As your organizer of this fundraiser, I plan to reach my goal to the best of my ability and show the donors how this will make a difference in these children lives. I will make sure community supporters are in place, tell them what we are doing, and commit to making the fundraiser a priority. Presenting this to a team of volunteers that’s eager to help, I want to let them know I will lead by example by sticking to the timeline and making a serious effort for this fundraiser to be a success.

I plan to take on a transformational style of leadership, I have elected a team leader to assist with the different components of a fundraiser. All staff has been introduced to a vision of how the event should be handled and agree upon having realistic fundraising goals and strategies. “Personally, I think setting goals together is important, however, having regular meetings to evaluate progress is as equal important so we as a team can decide how to reach the goal.” (What does a fundraising mananger do?, 2021)

As the organizer of this fundraiser, I want to make sure everyone know why theses funds are being raised. All volunteers will report to me, as stated previously I will oversee all of the fundraising functions. My responsibility of managing the volunteers, developing donors, interacting with the public, and creating effective strategies for increased donations will not be taken lightly. “Staying in contact and aware of complications will not only solve problems but make a true leader” (Cahalane, 2017). Last, but least thank everyone for participation and donating for such a special reason.

Conclusion

In conclusion, creating a fundraiser is a great way to secure and promote the community to come together for a great cause. Planning and organizing a successful fundraiser are a key and by utilizing the resources at hand such as the goods, services, and location local businesses and organizations have provided us, my team and I will work together to ensure a successful event. The important lesson taken away that is anything is possible with a little work, teamwork makes the dreamwork.

References

Cahalane, M. (2017). How you can keep fundraising staff happy and effective. Hands on Fundraising.

What does a fundraising mananger do? (2021). CareerExplorer by Sokano. https://www.careerexplorer.com