## WEEK 2 WORK BREAKDOWN
| 1.1 | 1.2 |  | 1.3 |  |  | 1.4 |  | 1.5 | 1.6
ARRANGE DJ |  | CHARCUTERIE APPETIZER |  | BOOTH FOR TOYS |  | INVITES FOR GUESTS |  | SERVERS FOR EACH TABLE |  | LIVE MUSIC DJ
| 1.1.1 |  | 1.2.1 |  | 1.3.1 |  | 1.4.1 |  | 1.5.1 |  | 1.6.1
ARRANGE GAMES |  | OPEN BAR |  | TABLES AND CHAIRS FOR DINNER |  | 250 PERSON PARTY |  | 10 BARTENDERS |  | MESSAGE FROM THE HOST
| 1.1.2 |  | 1.2.2 |  | 1.3.2 |  | 1.4.2 |  | 1.5.2 |  | 1.6.2
SET UP TOY BOOTH |  | CHAMPAGNE TOAST |  | BAR EQUIPMENT |  | FAMILIES ARE ALLOWED TO BRING KIDS |  | CLEAN UP STAFF |  | Q&A FOR TOY MAKER
| 1.1.3 |  | 1.2.3 |  | 1.3.3 |  | 1.4.3 |  | 1.5.3 |  | 1.6.3
TABLE SET DINNER |  | 3 COURSE DINNER |  | LIGHTS AND CAMERAS |  | TOY RAFFLES FOR GUESTS |  | BOOTH WORKERS
| 1.1.4 |  | 1.2.4 |  | 1.3.4 |  | 1.4.4 |  | 1.5.4
GUEST SPEAKERS |  | DESSERT BUFFET TABLE |  | BANQUET RENTAL (ROOM) |  | VALET FOR CARS |  | LIVE DJ
| 1.1.5 |  | 1.2.5 |  | 1.3.5 |  | 1.4.5 |  | 1.5.5
TOY LAUNCH EVENT
PLAN
DINNER
ROOM/EQUIPMENT
GUESTS
STAFF
SPEAKERS ETC.

## Wk 3 - Brainstorming Timeline
2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-15 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-31 | 2022-04-01
Arrange DJ and guest speakers.
Send out invites to the guests
Set up toy booth for the party.
Arrange servers, bartenders, and drivers for guests.
Reserve catering company for party. Make menu
Sparkle Party Planning
Order drinks and alochol for the bar.
PARTY TIME!
Set up banquet for party tomorrow
Set up area for kids to play
Arrange raffles

## Wk 4 - Gantt Chart
PROJECT TIMELINE
Enter the date of the first Monday of each month ----> | Q1 | [14 empty] | Q2 | [13 empty] | Q3 | [12 empty] | Q4
| JANUARY |  |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER
| 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 34 | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25
PROJECT WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PHASE ONE
Project Initiation
PHASE TWO
Project Planning
PHASE THREE
Project Execution
PHASE FOUR
Project Performance
PHASE FIVE
Project Close
TODAY
Find Dj and get quote
Arrange for games at the party (cornhole etc)
Set up Main booth attraction for Toys
Find out what desired outcome of the party is
Determine budget for the party
Finish guest list and create invites
Plan the meal for the guests
Arrange valet and nanny's for the party
Book guest speakers
Prepare host for a speech to the party
Book DJ, Catering, Furniture, and Clean up crew
Determine meal choices for guest and let catering company know
Send out invites and compile RSVP's
Live Camerman filming and photographing party
3 course Dinner with Dessert buffet
Live entertainment and guest speakers
Message from the host, followed by toy making Q&A
Send thank you cards to guests
File all billing to respective companies
Thank the host for using our company to help plan their party
Begin making guest list (250 guests)
Compile all billing and find total cost for the party.
PROJECT END

## Wk 5 - Expenses
Sparkle Party Planning |  |  | [Date]
Event Budget for Toy Makers Party: EXPENSES
Site | Estimated | Actual | Estimated vs. Actual
Banquet fees | 1000 | 1200
Servers, Bartenders, DJ | 1500 | 1700
Booth for toys | 600 | 500
Tables and chairs | 1000 | 500
Total | 4100 | 3900
Decorations | Estimated | Actual
Toys | 0 | 0
Disco Ball & lasers | 200 | 150
Lighting | 200 | 150
Balloons | 100 | 100
Life-size toy models | 700 | 500
Total | 1200 | 900
Publicity | Estimated | Actual
RSVP's | 1000 | 750
Photocopying/Printing | 500 | 500
Postage | 350 | 200
Total | 1850 | 1450
Miscellaneous | Estimated | Actual
Videographer | 750 | 650
Transportation | 1500 | 1750
Invite Supplies | 750 | 500
Raffle | 100 | 200
Total | 3100 | 3100
Refreshments | Estimated | Actual
Food | 4000 | 3780
Drinks/Alcohol | 5000 | 5400
Linens | 300 | 250
Staff and gratuities | 2500 | 2500
Total | 11800 | 11930
Program | Estimated | Actual
Live DJ | 500 | 350
Speakers | 2000 | 1750
Designated Drivers | 800 | 1000
Hotel option for guests | 1400 | 950
Other | 500 | 200
Total | 5200 | 4250
Prizes | Estimated | Actual
Toy Give away | 250 | 500
Goodbye Gifts | 500 | 375
Total | 750 | 875
Total Expenses | Estimated | Actual
| 28000 | 26405
Made in Office 2007 for office2007.com