## General
Team Name: | BEACH TRADE
Week: | 12

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Implement a way for the user to create a feed post that lists the item they are trying to sell
2 | Implement a new pop up window or activity that runs when the post feed button is pressed
3 | Allow users to enter their item description in the fiels provided and send that information back to the prevous fragment.
4 | Create layout for item view, card view, recycler view, feedpostview
5 | Implement a delete method for the cards
6 | Implement new item submission functionality
7 | Allow users to view their posted items and keep track of buyers
8
B. | List dependencies or things/decision that you waiting for in this week
1 | How should we design the layout for the Item Submission page
2 | How to implement aws s3 bucket features for profile pictures and item pictures
3 | How to implement search for users
4
5
C. | List your accomplishments from the previous week
1 | AWS Device Farm testing is functional with our app for all acitivities
2 | Figured out how we are going to implement social media post features
3 | Discovered how to tie dynamoDB functionality with cards in cardview
4
5
6
7
8

## Risk
Top Project Risks as of 11/16/2017
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Implementation of lambda fuctions | Research use of Lambda
2 | 2 | App crashing when certain fragments are loaded | Resaerch how to implement an offline mode
3 | 3 | Failure to load items correctly from dynamoDB | Experiement with how to get multiple items with DynamoDB
4 | 4 | Profile picture size uploaded to app too big and causes slowdown | Figure out how to limit picture size and type
5 | 5 | App crashing when syncing to dynamo db | Offline mode needed
6 | 6 | Failure to link the posted item to separate users | Make sure the item is tied to each unique identity
7 | 7 | Failure to unlink posted item | Make sure the posted item and all of its assets is erased
0 | 8 | Unlinked item continuing to display in database | Make sure the item is erased if it is not present in the the cardview. Recyclerview must keep refreshing to show changes.
0
0

## COTS
List of third-party components being considered for use in the system as of 11/16/2017
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
DynamoDB | Database | internet | developer
Lambda | Extends other AWS services | internet | developer
Cognito | User-Sign In System | internet | user
Amazon SES | Messaging System | internet | user
Github | Code repo | internet | developer
S3 | Storing Files | internet | user
AWS SDK | Code Implementation of AWS | interenet | developer

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | CardView text not displaying within the field of the card | Redesign the card view layout and make sure the textview match the parent
2 | Current main page design may not allow for organized pages | Redesign main page layout
3 | Clicked card in recycler view not sending data to new fragment | Research code implementation for this task
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | AWS Java SDK may be harder to implement than initially believed | Continuation of research of AWS Java SDK
2 | App crashing when quickly switching phone view modes | Research what could cause a crash when the phone is held in certain positions
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | CodeDeploy, Lambda, and DynamoDB understanding may be hard to grasp. | Meet more often to do group research on these services.
2 | Unsure about fragment designs | Revisit fragment classes layout
3 | How cloudformation templates work with our codepipeline
4
5