## General
Team Name: | BEACH TRADE
Week: | 14

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Get CodePipeline working
2 | Focus on AWS services like cloud formation
3 | Implement email and notification activity for user
4 | Fix the overall layout of the navigation bar
5 | Populate the navigation bar user information with the information that was sent to DyamoDB
6 | Prevent the applications home login screen from popping up after a user has already been verified
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | How to implement code deploy- outside classroom help
2 | How to connect BeachTrade to our existing S3 bucks for file storage
3 | How to implement categories for items
4
5
C. | List your accomplishments from the previous week
1 | Solved issues with DynamDB not correctly populating user credentials
2 | Implemented framgent in Navigation Bar for contacting
3 | Figured out our design for handling contacting and notifying sellers
4
5
6
7
8

## Risk
Top Project Risks as of 11/30/2017
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | App slowdown and crashing due to rendering issues | Research how to set limitations for picture sizes
2 | 2 | BeachTrade user falsifying their email to buyers | Resaerch how add email verification to user input email
3 | 3 | Failure to load items correctly from dynamoDB | Experiement with how to get multiple items with DynamoDB
4 | 4 | App crashing when undergoing unit testing | Include a guest profile
5 | 5 | Failure to properly display a user's email | Research how to send DynamDB info thorugh activities
6 | 6 | Failure to link the posted item to separate users | Make sure the item is tied to each unique identity
7 | 7 | Failure to unlink posted item | Make sure the posted item and all of its assets is erased
0 | 8 | Unlinked item continuing to display in database | Make sure the item is erased if it is not present in the the cardview. Recyclerview must keep refreshing to show changes.
0
0

## COTS
List of third-party components being considered for use in the system as of 11/30/2017
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
DynamoDB | Database | internet | developer
Lambda | Extends other AWS services | internet | developer
Cognito | User-Sign In System | internet | user
Amazon SES | Messaging System | internet | user
Github | Code repo | internet | developer
S3 | Storing Files | internet | user
AWS SDK | Code Implementation of AWS | interenet | developer

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | User inputting a wrong email | Verify the email stored in DynamoDB matches FaceBook email
2 | Changes to profile information on facebook not taking effect in app | Research way to handle this with facebook api
3 | User inputted email not linking to their card post | Grab the email directly from DynamoDB
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | App continuosly crashing when entered in Device Farm | Figure out a way to get unit testing working without cognito identity
2 | App crashing when quickly switching phone view modes | Research what could cause a crash when the phone is held in certain positions
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | CodeDeploy, Lambda, and DynamoDB understanding may be hard to grasp. | Meet more often to do group research on these services.
2 | Unsure about fragment designs | Revisit fragment classes layout
3 | How cloudformation templates work with our codepipeline
4 | Time managementt problems with finals and other projects | Get design and sprint 4 implementations completed before tackling AWS services
5