## General
Team Name: | BEACH TRADE
Week: | 6

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Revisit User Stories
2 | Revisit CodePipeline and Deployment Automation
3 | Research implementation of AWS Java Android SDK
4 | Revisit UML/Class diagrams
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | How to distribute work amongst team
2 | What services/design our team will use to make the app a success
3 | How to implement missed targets that was to be included in our first user story
4 | How we are going to tie the missed attributes into our second user story
5
C. | List your accomplishments from the previous week
1 | GitHub AutoDeploy is in working order
2 | Researched MobileHub implementation
3 | Basic UML/Class diagrams completed.
4 | Learned how to apply implemetations to make second sprint much simpler and easier
5
6
7
8

## Risk
Top Project Risks as of 09/28/2017
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | N/A | Implementation of lambda fuctions
2 | N/A | Storing files and uploaded pictures to server
3 | N/A | Failure to sign in to application
4 |  | Implementation of AWS Cognito not displaying or showing our customized UI
5
0
0
0
0
0

## COTS
List of third-party components being considered for use in the system as of 09/28/2017
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
DynamoDB | Database | internet | developer
Lambda | Extends other AWS services | internet | developer
Cognito | User-Sign In System | internet | user
Amazon SES | Messaging System | internet | user
Github | Code repo | internet | developer
S3 | Storing Files | internet | user
AWS SDK | Code Implementation of AWS | interenet | developer

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | n/a | n/a
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | AWS Java SDK may be harder to implement than initially believed | Continuation of research of AWS Java SDK
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | CodeDeploy, Lambda, and DynamoDB understanding may be hard to grasp. | Meet more often to do group research on these services.
2 | Sprints may have work unevenly distributed | Possibly work on next sprint's user stories if current goals reached.
3
4
5