## General
Team Name: | BEACH TRADE
Week: | 9

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Create List view for items on Main Page
2 | Implement list functionality with DynamoDB
3 | Implement search functionality for items
4 | Research fragment layouts/ fix broken fragments
5 | Implement S3 bucket link to uploaded pictures
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Should we Implement username/password login, in addition to Facebook login
2 | How to Design the User Profile Layout
3 | Cognito email verification
4 | User profile link to dynamo db
5
C. | List your accomplishments from the previous week
1 | AWS CodePipeline is Functional
2 | New user username setup is working
3 | Device farm test without facebook login to test rest of activities.
4
5
6
7
8

## Risk
Top Project Risks as of 11/4/2017
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Implementation of lambda fuctions | Research use of Lambda
2 | 2 | Storing files and uploaded pictures to server | Research implementation of S3 bucket storage access
3 | NA | Failure to load items correctly from dynamoDB | Experiement with how to get multiple items with DynamoDB
4 | 4 | Profile Implementation may not work | Continue work on profiles
5 | 5 | App crashing when syncing to dynamo db
6 | 6
7
0
0
0

## COTS
List of third-party components being considered for use in the system as of 09/28/2017
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
DynamoDB | Database | internet | developer
Lambda | Extends other AWS services | internet | developer
Cognito | User-Sign In System | internet | user
Amazon SES | Messaging System | internet | user
Github | Code repo | internet | developer
S3 | Storing Files | internet | user
AWS SDK | Code Implementation of AWS | interenet | developer

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Device Farm stuck cannot get past Facebook Login | Remove facebook login for testing purposes.
2 | Layout of main activity may be broken | Research fragment layout implementation
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | AWS Java SDK may be harder to implement than initially believed | Continuation of research of AWS Java SDK
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | CodeDeploy, Lambda, and DynamoDB understanding may be hard to grasp. | Meet more often to do group research on these services.
2 | May be hard to implement regular login | Ask other groups for help on implementation of username/password login
3
4
5