Process for

Combined Public Notice

(or Finding of No Significant Impact and

Notice of Intent to Request Release of Funds)

Under a Full Assessment Project

Step 1 - Complete the environmental review (compliance with 24 CFR Part 58.5 and 6 and NEPA) and attach all documentation. Recommend FONSI to Certifying Official.

Step 2 - Certifying Official signs FONSI prior to publication/posting date of Combined Notice (CN), or Finding of No Significant Impact (FONSI) and Notice of Intent to Request Release of Funds (NOI/RROF).

Step 3 - Publish or post CN (or FONSI and NOI/RROF). There is a 15-day comment period for publishing and 18-day comment period for posting. (NOTE: You cannot count the day of publication/posting when calculating the days.)

Step 4 - Have Certifying Official sign and date the “Request for Release of Funds and Certification” the day after the comment period expires.

Step 5 - Email the complete Environmental Assessment to the State (and mail a hard copy with original signatures).

Step 6 – State begins to count the 15-day comment period the day after receipt of the Environmental Assessment.

Step 7 – After the 15-day comment period is up, the State removes the grant condition and the funds are released.

Example of Timing for a Published NOI/RROF

1. Date of Public Notice (Publish or Post): May 1

2. Time period for receipt of public comments: May 2 to May 16

3. Deadline date for local government comment period indicated in notice: May 16

4. Earliest date to submit to HUD: May 17

5. Earliest date to be received by HUD: May 17

6. Statutory 15-day HUD comment period: May 18 to June 1

7. Deadline date for receipt by HUD of Objections to release of funds: June 1

8. Earliest possible notice from HUD that funds are released: June 2

Source:  HUD Environmental Training Manual CD-ROM version 3.0