# Project Update: Launching “Featured Product” Box

Prepared by Andrew Blackman, 16 March 2015

The launch of the new “featured product” box on the corporate website is still on track for 30 April.

- Coding was completed ahead of schedule, and beta version was launched to limited number of customers.

- Trial showed a 12.7% click-through rate, and has already generated an additional $5,000 in sales.

- We still need to get agreement from sales managers on which products to feature. This is proving more difficult than anticipated.

## Progress Against Milestones

The following chart shows our progress on the key project milestones:

Coding and testing are ahead of schedule, but agreements with sales and legal teams are behind schedule. Overall the project remains on track.

## Key Issues

Two issues need to be resolved for the project to meet its deadline:

- Sales managers remain unconvinced about the feature, and can’t agree on which products should be featured. I’ve planned a meeting with them on 10 April, and would like you to attend to help win them over.

- Legal team needs to give approval. This should be a formality, but is moving more slowly than expected.

## Action Steps

| Task | Due Date | Responsibility |
| --- | --- | --- |
| Hold meeting with sales managers to finalise agreement on products to feature. | 10 April | AB/JD |
| Complete testing of website feature | 20 April | AB |
| Finalise legal approvals | 23 April | AB/GC |
| Launch new feature on website | 30 April | AB |