## 2018 NCCUSL activities
NorCal Chapter of US Lacrosse, Inc.
| 2018 key NorCal Chapter activities/initiatives | Objective | Primary person responsible | Planned Time frame | Date(s) | Projected Income | Projected Expense | Comments
1 | California Lacrosse Convention | Provide additional learning opportunities for coaches and administrators | TBD - Initial leadership interest from Nolan Godfrey (Novato HS) & Jim Kircher (Petaluma club) | Jan 6 or 7 |  | 8250 | 8250 | Objective is to at least break even. Jan 6 or 7 look best. Evaluate venues now. Nolan and Godfrey indicate that they may have some men's game speakers lined up. DTA to review. Not sure if Nolan can line up women's game speakers. May need help.
2 | CEP sessions; 8 level 1's (new short course) for men and women; 1 level 2 | Provide CEP clinics to support league and national requirements for certified coaches. 8 new level 1 clinics; 1-2 Level 2's | Lou Biaggi | Jan/Feb |  |  | 3800 | Chapter in conjunction with NCJLA to reach out to clubs to determine interest. Only establish clinics if interest from a club and NCJLA support.
3 | Additional onsite coach training | Provide additional onsite training for coaches | TBD | As requested |  |  | 600 | Utilize Lorne Smith, ADVNC, Encore, Tenacity and other professional coaches and organizations; 3 clinics; need to find a reliable coordinator familiar with good professional coaches
4 | Outreach | Provide sticks and guidance to individuals and programs that want to have clinics and or establish or expand lacrosse in their geography | Don, Brian, Phil & Ian | Year round |  |  | 4000 | Direct costs include storage unit, shipping sticks and new stick purchases.
5 | Non traditional area sport development | Establish one new lacrosse program in a non traditional area | Brian Atwell, Phil Bodenhorn & DTA | Ongoing |  |  |  | Continue 2017 diversity and expansion initiatives. Reach out to Lacrosse community to determine which programs could benefit with financial or material support. Assume D&I grant funds received from USL will be granted out to deserving programs.
6 | National team clinics | Provide additional training opportunities for boys & girls in the chapter; expand awareness of chapter's role in supporting lacrosse | TBD | TBD |  |  |  | If men & women's national team players are available hold session(s) in NorCal. No income or expenses budgeted. DTA to follow up with Onuva Chowdhury.
7 | Constituent support meeting | Develop understanding of key constiuents' needs as a basis for developing the chaper budget | Don | June |  |  | 450 | Meeting room and refreshment costs included in travel and meeting expenses
8 | Support Officials' evaluations and officials trainer development programs | Provide funds to men and women officials' organization so trainer officials can take time to evaluate on field officials with the expectation that the level of officiating overall rises. | Andy Still - NCRLA; Tyronne Koen and/or Laura Jennings for Umpire Committee of NCCUSL | Mar/Apr |  |  | 2500 | Assumes $1,500 for NCRLA and $1,000 for NCCUSL Umpire Committee or successor
9 | Support USL All American process | Support USL All American process so local athletes obtain recognition | Amy Harms/Nick Juri/Jerem Stothers/Bruce Dini - dogged by Phil B; Chapter publicity - Torri H | May/June |  |  |  | Receipents announced and published on the NorCal website and newsletter in June.
10 | Maintain website & newsletter | Broad communications | Torri Horowitz; Dan Miller; Don Aiello | Jan-Dec |  |  | 500 | Website - load material and programs; 8 newsletters
11 | Participate in key league and local lacrosse events, e.g., Girls Play Day or equivalent (Davis and/or TI); NCJLA end of season events (May); NCJLA Delegates mtg (Sept); | Develop and expand awareness of Chapter and USL programs and services | Chapter board members as available | Feb, Mar, May, Sept | Feb, Mar, May, Sept |  | 1000 | Costs would include travel and meeting expenses. Moving the Chapter booth; Production of flyers and chapter logoed giveaways. Stocked items from 2016 would carryover/be available
12 | HOF recognition dinner | Recognition of HOF recipients; further opportunity to expand the awareness of Chapter | TBD for process; Jeanette for venue; Don, other details | Sept/Oct |  | 6400 | 9000 | 10 inductees; 80 paid guests @ $80 each
13 | Additional board members and committee volunteers | Add 1-3 more board members and key activity volunteers. POCO rep; HS boys and girls reps; board development chair; Events coordinator; | Don | Ongoing |  |  | 800 | Shirts, hats, awards, meals
14 | Oversee NorCal Chapter Umpire Committee | Continue UC operations under the chapter through mid-year and then plan to spin it out to its own organization. | Don, Laura, Tyrone (?) & Stephen | Jan-June |  | TBD - Budget under contruction | TBD - Budget under contruction | For 2018 continue operations. Assist with spin off of UC to separate organization mid year 2018
| USL Train NorCal Chapter trainers | Provide Chapter certified level 1 trainers | [5 empty] | Presuming this will be completed in 2017
Deliever Education Training
Support Local Lacrosse Organizations
Fuel the Growth of the Sport
Drive Chapter Visibility
Other