##  2021 ILSPAN STRATEGIC PLAN – Updated 3/5/2021

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| GOAL | **INITIATIVES** | **RESPONSIBILITY** | **DUE DATE** | **STATUS** |
| **GOAL A: ILSPAN will be its members’ indispensable resource for peri-anesthesia education and knowledge exchange.** |
| **A-1** | *Promote educational programs to other specialty practices** Continue to collaborate with other professional organizations to provide ILSPAN educational offerings
 | BOD/Technology |  July 2021 | In Progress |
| **A-2** | *Coordinate ASPAN Seminars in all three districts, and promote ASPAN Webinars** Promote ASPAN webinars at general membership meeting
* Propose one Winter/Spring seminar
* Propose one Summer/Fall seminar
 | PresidentDD 2DD3 |  October 2021July 15, 2021February 15, 2022 | In ProgressIn ProgressIn Progress |
| **A-3** | *Increase awareness of ILSPAN/ASPAN educational programs, services, and scholarships.* * Pursue marketing strategies to expand general membership
* ILSPAN conference student scholarship
 | BODBOD | July 2021July 2021 | In ProgressIn Progress |
| **GOAL B: ILSPAN, in conjunction with ASPAN will be the acknowledged advocate for peri-anesthesia patient safety, public policy and practice standards in the state of Illinois and Eastern Missouri.**  |
| **B-1** | *Publish newsletter articles focusing on Clinical Issues** Spring/Summer – The Spirit of Inquiry
* Fall 2021 – Spinal Anesthesia Postop Assessment
* Winter 2022 – topic TBD
 | SecretaryDD2Vice President |   April 1, 2021August 15, 2021 December 1, 2021 | In ProgressIn ProgressIn Progress |
| **B-2** | *Promote excellence in peri-anesthesia practice** Nominate Jan Ridder applicant
* Increase members’ awareness of available ASPAN/ILSPAN resources to educate and support clinical practice
 | BODBOD/Technology Chair | November 15, 2021July 2021 | In ProgressIn Progress |
| **GOAL C: ILSPAN, in conjunction with ASPAN, will be the recognized face of peri-anesthesia information to the public in the state of Illinois and eastern Missouri.**  |
| **C-1** | *Promote Humanitarian Scholarship to members** Review ASPAN Humanitarian Scholarship recipient, if ILSPAN member, forward ILSPAN Humanitarian Scholarship application
 | BOD/Vice-President | July 1, 2021 | In Progress |
| **C-2** | *Participate in/support community program or project* * Organize an annual community-based volunteer charity event of their choice
 | DD2/DD3 | October 2021 | In Progress |
| **GOAL D: ILSPAN will advocate evidence-based practice and peri-anesthesia research activities.** |
| **D-1** | *Provide education on the research process on-line and in newsletter** Review Research poster presentations at National Conference to obtain future *Peri-Scope* articles
* Canvas ILSPAN members for current research projects and support their efforts requesting written article for *Peri-Scope* thus creating guest columnist
 | Research Chair/Publications ChairResearch Chair/Publications Chair | May 2021July 2021 | In ProgressIn Progress |
| **D-2** | *Provide education on evidence-based practices** Review CSP poster presentations during virtual national/local conference to obtain future *Peri-Scope* articles.
* Review conference evaluations to obtain future *Peri-Scope* articles.
 | Research Chair/Publication ChairPublication Chair/Research Chair | May 2021April 2021 | In ProgressIn Progress |
| **D-3** | *Provide updates on current peri-anesthesia research/CSP at each meeting (BOD, general membership) and in newsletter* * CSP Posters displayed at Fall and Spring Conference
* Research posters displayed at Fall and Spring Conference
* Evaluate additional posters for presentation at ILSPAN conferences
 | General MembershipGeneral MembershipResearch Chair |  Spring 2021, Fall 2021 Spring 2021, Fall 2021 Spring 2021, Fall 2021 | In ProgressIn ProgressIn Progress |
| **E: INFRASTRUCTURE: governance / membership / Customer Service** |
| **Governance** | *Promote and develop leadership within ILSPAN, mentor new Component Leaders* * Succession Planning for all ILSPAN Board Committees
* Invite general members to BOD meetings to encourage involvement in BOD/Committees via Facebook, website and personal invites
* Include general members to attend ASPAN LDI
 | BODBOD BOD | July 2021July 2021July 2021 | In ProgressIn ProgressIn Progress |
| **Members** | *Increase membership with effective recruitment and retention** Expand current Manager, Unit Educator, and Research Coordinator contact lists on website for use in promoting ILSPAN
* Create Marketing Chair job description
 | BODBOD | July 2021July 2021 | In ProgressIn Progress |
| **Service** | *Collaborate with schools of nursing to promote awareness of perianesthesia nursing* * Continue to update and revise School of Nursing contacts in ILSPAN area on website contact list
* Send save the date notices and brochures of ILSPAN conference to contact lists
 | Education/Technology ChairsEducation Chair  | July 2021July 2021 | In ProgressIn Progress |
| **Operations** | *Explore e-commerce and technology options for conferences/scholarships** Evaluate effectiveness of electronic post-conference evaluations and contact hour certificate distributions.
* Explore expanding ILSPAN website to manage post-conference evaluations and contact hour certificate distributions
* Implement storage options for ILSPAN documents with Gmail accounts/Google drive
 | Technology/ Education ChairsTechnology ChairPublications Chair | July 2021July 2021July 2021 | In ProgressIn ProgressIn Progress |