## 2021 ILSPAN STRATEGIC PLAN – Updated 3/5/2021

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| GOAL | **INITIATIVES** | **RESPONSIBILITY** | **DUE DATE** | **STATUS** |
| **GOAL A: ILSPAN will be its members’ indispensable resource for peri-anesthesia education and knowledge exchange.** | | | | |
| **A-1** | *Promote educational programs to other specialty practices*   * Continue to collaborate with other professional organizations to provide ILSPAN educational offerings | BOD/Technology | July 2021 | In Progress |
| **A-2** | *Coordinate ASPAN Seminars in all three districts, and promote ASPAN Webinars*   * Promote ASPAN webinars at general membership meeting * Propose one Winter/Spring seminar * Propose one Summer/Fall seminar | President  DD 2  DD3 | October 2021  July 15, 2021  February 15, 2022 | In Progress  In Progress  In Progress |
| **A-3** | *Increase awareness of ILSPAN/ASPAN educational programs, services, and scholarships.*   * Pursue marketing strategies to expand general membership * ILSPAN conference student scholarship | BOD  BOD | July 2021  July 2021 | In Progress  In Progress |
| **GOAL B: ILSPAN, in conjunction with ASPAN will be the acknowledged advocate for peri-anesthesia patient safety, public policy and practice standards in the state of Illinois and Eastern Missouri.** | | | | |
| **B-1** | *Publish newsletter articles focusing on Clinical Issues*   * Spring/Summer – The Spirit of Inquiry * Fall 2021 – Spinal Anesthesia Postop Assessment * Winter 2022 – topic TBD | Secretary  DD2  Vice President | April 1, 2021  August 15, 2021  December 1, 2021 | In Progress  In Progress  In Progress |
| **B-2** | *Promote excellence in peri-anesthesia practice*   * Nominate Jan Ridder applicant * Increase members’ awareness of available ASPAN/ILSPAN resources to educate and support clinical practice | BOD  BOD/Technology Chair | November 15, 2021  July 2021 | In Progress  In Progress |
| **GOAL C: ILSPAN, in conjunction with ASPAN, will be the recognized face of peri-anesthesia information to the public in the state of Illinois and eastern Missouri.** | | | | |
| **C-1** | *Promote Humanitarian Scholarship to members*   * Review ASPAN Humanitarian Scholarship recipient, if ILSPAN member, forward ILSPAN Humanitarian Scholarship application | BOD/Vice-President | July 1, 2021 | In Progress |
| **C-2** | *Participate in/support community program or project*   * Organize an annual community-based volunteer charity event of their choice | DD2/DD3 | October 2021 | In Progress |
| **GOAL D: ILSPAN will advocate evidence-based practice and peri-anesthesia research activities.** | | | | |
| **D-1** | *Provide education on the research process on-line and in newsletter*   * Review Research poster presentations at National Conference to obtain future *Peri-Scope* articles * Canvas ILSPAN members for current research projects and support their efforts requesting written article for *Peri-Scope* thus creating guest columnist | Research Chair/Publications Chair  Research Chair/Publications Chair | May 2021  July 2021 | In Progress  In Progress |
| **D-2** | *Provide education on evidence-based practices*   * Review CSP poster presentations during virtual national/local conference to obtain future *Peri-Scope* articles. * Review conference evaluations to obtain future *Peri-Scope* articles. | Research Chair/Publication Chair  Publication Chair/Research Chair | May 2021  April 2021 | In Progress  In Progress |
| **D-3** | *Provide updates on current peri-anesthesia research/CSP at each meeting (BOD, general membership) and in newsletter*   * CSP Posters displayed at Fall and Spring Conference * Research posters displayed at Fall and Spring Conference * Evaluate additional posters for presentation at ILSPAN conferences | General Membership  General Membership  Research Chair | Spring 2021, Fall 2021  Spring 2021, Fall 2021  Spring 2021, Fall 2021 | In Progress  In Progress  In Progress |
| **E: INFRASTRUCTURE: governance / membership / Customer Service** | | | | |
| **Governance** | *Promote and develop leadership within ILSPAN, mentor new Component Leaders*   * Succession Planning for all ILSPAN Board Committees * Invite general members to BOD meetings to encourage involvement in BOD/Committees via Facebook, website and personal invites * Include general members to attend ASPAN LDI | BOD  BOD  BOD | July 2021  July 2021  July 2021 | In Progress  In Progress  In Progress |
| **Members** | *Increase membership with effective recruitment and retention*   * Expand current Manager, Unit Educator, and Research Coordinator contact lists on website for use in promoting ILSPAN * Create Marketing Chair job description | BOD  BOD | July 2021  July 2021 | In Progress  In Progress |
| **Service** | *Collaborate with schools of nursing to promote awareness of perianesthesia nursing*   * Continue to update and revise School of Nursing contacts in ILSPAN area on website contact list * Send save the date notices and brochures of ILSPAN conference to contact lists | Education/Technology Chairs  Education Chair | July 2021  July 2021 | In Progress  In Progress |
| **Operations** | *Explore e-commerce and technology options for conferences/scholarships*   * Evaluate effectiveness of electronic post-conference evaluations and contact hour certificate distributions. * Explore expanding ILSPAN website to manage post-conference evaluations and contact hour certificate distributions * Implement storage options for ILSPAN documents with Gmail accounts/Google drive | Technology/ Education Chairs  Technology Chair  Publications Chair | July 2021  July 2021  July 2021 | In Progress  In Progress  In Progress |