## 2015 – 2016 ILSPAN STRATEGIC PLAN – Final 1/9/2016

| # GOAL | initiatives | responsibility | due date | status |
| --- | --- | --- | --- | --- |
| GOAL A: ILSPAN will be its members’ indispensable resource for perianesthesia education and knowledge exchange. |  |  |  |  |
| A-1 | Develop and present new educational programs sponsored by ILSPAN to enhance knowledge exchange - Identify perianesthesia nurses’ educational needs, obtain education needs from conference evaluations | Education Committee | Fall Conference-TBD 2016 | In Progress |
| A-2 | Establish educational programs in conjunction with other professional organizations and specialty practices - Looking for partnership with another professional organization to develop educational offering | Education Committee | October 2016 | In Progress |
| A-3 | Coordinate ASPAN Seminars in all three districts, and promote ASPAN Webinars - Promote ASPAN webinars at general membership meeting - Propose one Winter/Spring seminars - Propose one Summer/Fall seminars | BOD | March 2016 July 2016 February 2016 | In Progress |
| A-4 | Increase awareness of ILSPAN/ASPAN educational programs, services, and scholarships. - Task force to develop marketing strategies - Continue to create contact person at hospitals within ILSPAN territory | BOD | March 2016 March 2016 | In Progress In Progress |
| GOAL B: ILSPAN, in conjunction with ASPAN will be the acknowledged advocate for perianesthesia patient safety, public policy and practice standards in the states of Illinois and Eastern Missouri. |  |  |  |  |
| B-1 | Promote standards of perianesthesia practice in the clinical setting - Present ASPAN Standards 2015-2017 as attendance prize at annual conferences. | Vice President | March & October 2016 | Ongoing |
| B-2 | Publish newsletter articles focusing on Clinical Issues - Legal Issues/Illinois - Regional Blocks - Use of Capnography | Publication Committee General Membership BOD | September 2016 | In progress |
| B-3 | Promote excellence in perianesthesia practice - Submit name of Jan Ridder Excellence Award nominee - Submit name of Clinical Excellence Award recipient to ASPAN for consideration of the Excellence in Clinical Practice ASPAN Award (policy requires revision on submission date) - Develop increased awareness of PANAW, including gifts, etc. | President BOD BOD | October 2016 March 2016 | Pending Ongoing |
| GOAL C: ILSPAN, in conjunction with ASPAN, will be the recognized voice and source of perianesthesia information to the public in the state of Illinois and eastern Missouri. |  |  |  |  |
| C-1 | Educate ILSPAN membership regarding humanitarian scholarship - Review ASPAN Humanitarian Scholarship recipient, if ILSPAN member, forward ILSPAN Humanitarian Scholarship application | BOD General Membership Publication Committee | July 2016 | Pending |
| C-2 | Participate in/support community program or projects - Charitable donations, food items to be collected at conferences and distributed to local charities. - Charitable donations collected at National Conference to be donated to local charity accordingly. - Investigate and create list of creditable charities in each ILSPAN district | General Membership General Membership P.P. & District Directors | March 2016 April 2016 March 2016 | Ongoing Ongoing Pending |
| GOAL D: ILSPAN will advocate evidence-based practice and perianesthesia research activities. |  |  |  |  |
| D-1 | Provide education on the research process on-line, in newsletter - Research grant update article. - Review Research poster presentations at National Conference to obtain future Peri-Scope articles - Canvas ILSPAN members for current research projects and support their efforts requesting written article for Peri-Scope thus creating guest columnist. | Publication Committee Technology Committee & Research Committee Board of Directors | October 2016 April 2016 March 2016 | Pending Ongoing Pending |
| D-2 | Provide education on evidence-based practices - Review EBP poster presentations at National Conference to obtain future Peri-Scope articles. - Review conference evaluations to obtain future Peri-Scope articles. - Update educational resources via ILSPAN website | Publication Committee & BOD BOD BOD & Education Chair | April 2016 March 2016 September 2016 | Ongoing Pending Pending |
| D-3 | Provide updates on current perianesthesia research at each meeting (BOD, general membership) and in newsletter - Progress update about Sensitivity and Specificity of the At Risk Screening Tool for Emergency Events after Post Anesthesia Care Unit Discharge project (First recipient of the ILSPAN research grant has completed their research and are completing the article for JOPAN) - CSP Posters displayed at Spring and Fall Conference - Research posters displayed at Spring and Fall Conference | Research Grant recipients General Membership General Membership | Sept/Oct 2016 Spring 2016, Fall 2016 Spring 2016, Fall 2016 | Ongoing Ongoing Ongoing |
| E: INFRASTRUCTURE: membership / governance / Customer Service |  |  |  |  |
| Governance | Promote and develop leadership within ILSPAN, mentor new Component Leaders - Transition new board members. - Follow-up/evaluate mentorship and transition process by reviewing & completing checklist - Succession Planning for all ILSPAN Board Committees - Promote Leadership Development by attending ASPAN LDI | ILSPAN Board Committees & BOD BOD BOD BOD | March 2016 March 2016 September 2016 | In Progress In Progress In Progress In Progress |
| Members | Expand membership with effective recruitment and retention - Recognize longevity of perianesthesia certification at Spring Conference - Engage and develop member involvement on ILSPAN Committees | President BOD | March 2016 March 2016 | In Progress Ongoing |
| Service | Collaborate with schools of nursing to promote awareness of perianesthesia nursing - Promote Spring conference and ILSPAN Scholarships to schools of nursing - Continue to update and revise School of Nursing list/contacts in ILSPAN area | BOD General Membership Vice President | March 2016 March 2016 | Ongoing Ongoing |
| Operations | Explore e-commerce and technology options for conferences/scholarships - Investigate options for online handouts - Develop ongoing ILSPAN calendar on website - Engage membership to follow ILSPAN on Facebook - Develop strategies to increase usage of ILSAPN website & Facebook page - Survey members via needs assessment to identify educational needs & social media options for ILSPAN | Technology Committee PP/Technology Committee BOD BOD/ Technology Committee BOD | March 2016 March 2016 March 2016 March 2016 March 2016 | In Progress In Progress In Progress Pending Pending |