## WIP
Sample Contractor, Inc.
Work-in-Progress Schedule
As of | 2026-09-30
8 job(s) flagged - see the Issues column at the far right
|  |  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | CURRENT YEAR |  |  | BALANCE SHEET |  | CONTROLS
Job # | Description | Status | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings | Issues
2507 | Riverside Medical Office Building | In Progress | 2450000 | 2082500 | 367500 | 15% | 60% | 833000 | 1350000 | 1470000 | 1249500 | 220500 | 15% | 820000 | 700000 | 650000 | 549500 | 100500 | 120000 | 0
2512 | Canyon View Elementary - Phase 2 | In Progress | 4800000 | 4320000 | 480000 | 10% | 45% | 2376000 | 2100000 | 2160000 | 1944000 | 216000 | 10% | 0 | 0 | 2160000 | 1944000 | 216000 | 60000 | 0
2519 | Highway 89 Box Culvert Replacement | In Progress | 610000 | 540000 | 70000 | 11.48% | 105.7% | -31000 | 590000 | 645018.5185 | 571000 | 74018.5185 | 11.48% | 310000 | 265000 | 335018.5185 | 306000 | 29018.5185 | 55018.5185 | 0 | Cost to date exceeds estimated cost - job is over 100% complete; update the estimate
2521 | Summit Logistics Warehouse TI | In Progress | 1200000 | 1020000 | 180000 | 15% | 90% | 102000 | 1235000 | 1080000 | 918000 | 162000 | 15% | 0 | 0 | 1080000 | 918000 | 162000 | 0 | 155000 | Billings exceed the contract amount
2526 | Parkside Apartments - Building C | In Progress | 3150000 | 3290000 | -140000 | -4.444% | 60% | 1316000 | 1900000 | 1890000 | 1974000 | -84000 | -4.444% | 1100000 | 1200000 | 790000 | 774000 | 16000 | 0 | 10000 | Loss contract - the full expected loss must be recognized
2531 | Downtown Parking Structure Repairs | In Progress | 890000 | 712000 | 178000 | 20% | 20% | 569600 | 0 | 178000 | 142400 | 35600 | 20% | 0 | 0 | 178000 | 142400 | 35600 | 178000 | 0 | Costs incurred but nothing billed yet; Underbilled by more than 10% of the contract - look for unapproved change orders or unbilled work
2533 | Westgate Retail Shell | In Progress | 2000000 | 1700000 | 300000 | 15% | 75% | 425000 | 1450000 | 1500000 | 1275000 | 225000 | 15% | 1560000 | 1230000 | -60000 | 45000 | -105000 | 50000 | 0 | Prior-year revenue exceeds inception-to-date revenue
2418 | Lakeview Dental Clinic | Complete | 1480000 | 1310000 | 170000 | 11.49% | 100% | 0 | 1480000 | 1480000 | 1310000 | 170000 | 11.49% | 1000000 | 890000 | 480000 | 420000 | 60000 | 0 | 0
2422 | Fire Station 7 Addition | Complete | 2210000 | 1900000 | 310000 | 14.03% | 101.8% | -35000 | 2210000 | 2250710.5263 | 1935000 | 315710.5263 | 14.03% | 1500000 | 1300000 | 750710.5263 | 635000 | 115710.5263 | 40710.5263 | 0 | Marked Complete but estimated cost does not equal cost to date
2427 | Maple Grove Church Remodel | Complete | 760000 | 650000 | 110000 | 14.47% | 100% | 0 | 722000 | 760000 | 650000 | 110000 | 14.47% | 300000 | 260000 | 460000 | 390000 | 70000 | 38000 | 0 | Marked Complete but billings do not equal the contract amount
2535 | Eastside Water Line Extension |  | 540000 | 470000 | 70000 | 12.96% | 20% | 376000 | 120000 | 108000 | 94000 | 14000 | 12.96% | 0 | 0 | 108000 | 94000 | 14000 | 0 | 12000 | Status missing
| Totals - all jobs |  | 20090000 | 17994500 | 2095500 | 10.43% | 67.04% | 5931600 | 13157000 | 13521729.0448 | 12062900 | 1458829.0448 | 10.79% | 6590000 | 5845000 | 6931729.0448 | 6217900 | 713829.0448 | 541729.0448 | 177000
| of which In Progress |  | 15100000 | 13664500 | 1435500 | 9.507% | 59.09% | 5590600 | 8625000 | 8923018.5185 | 8073900 | 849118.5185 | 9.516% | 3790000 | 3395000 | 5133018.5185 | 4678900 | 454118.5185 | 463018.5185 | 165000
| of which Complete |  | 4450000 | 3860000 | 590000 | 13.26% | 100.9% | -35000 | 4412000 | 4490710.5263 | 3895000 | 595710.5263 | 13.27% | 2800000 | 2450000 | 1690710.5263 | 1445000 | 245710.5263 | 78710.5263 | 0
How to use this schedule
Enter | from the job cost report and general ledger
Enter | from the prior-year WIP schedule
Formula | calculated - do not type here
Red text | a control failed - the Issues column at the far right says what is wrong
Status drives the Contracts in Progress and Completed Contracts tabs. Those tabs rebuild themselves - never edit them.
To add jobs: right-click the blank row just above Totals, choose Insert, then copy the formulas down from the row above. Every total, control and tab picks up the new row automatically.
Underbillings and overbillings come from this schedule; the tie-out below compares the schedule to the general ledger.
| Tie-out to the general ledger | [14 empty] | CY revenue | CY cost |  | Underbillings | Overbillings
| Balance per general ledger | [14 empty] | 6931729 | 6217900 |  | 516729 | 177000
| Per this schedule (Totals row) | [14 empty] | 6931729.0448 | 6217900 |  | 541729.0448 | 177000
| Difference - must be zero |  | Schedule does not tie to the general ledger - find the difference before this WIP is issued | [12 empty] | 0 | 0 |  | -25000 | 0
| Loss contracts in progress |  |  |  | Estimated GP
| Total expected loss on in-progress loss contracts |  |  |  | -140000
| Loss already recognized through % complete |  |  |  | -84000
| Additional loss to accrue (provision for loss on contracts) |  |  |  | -56000 |  | Book an additional loss provision of 56,000 so the full expected loss is recognized this period
Prepared by Levvigo ¦ levvigo.com

## Contracts in Progress
Sample Contractor, Inc.
Schedule of Contracts in Progress
For the period ended September 30, 2026
|  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | CURRENT YEAR |  |  | BALANCE SHEET
Job # | Description | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings
| Totals - 7 contracts | 15100000 | 13664500 | 1435500 | 9.507% | 59.09% | 5590600 | 8625000 | 8923018.5185 | 8073900 | 849118.5185 | 9.516% | 3790000 | 3395000 | 5133018.5185 | 4678900 | 454118.5185 | 463018.5185 | 165000
0
This schedule is built from the WIP tab by one FILTER formula in cell B9 - change a job's Status on the WIP tab and it moves here on its own. Nothing on this tab needs editing.

## Completed Contracts
Sample Contractor, Inc.
Schedule of Completed Contracts
For the period ended September 30, 2026
|  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | CURRENT YEAR |  |  | BALANCE SHEET
Job # | Description | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings
| Totals - 3 contracts | 4450000 | 3860000 | 590000 | 13.26% | 100.9% | -35000 | 4412000 | 4490710.5263 | 3895000 | 595710.5263 | 13.27% | 2800000 | 2450000 | 1690710.5263 | 1445000 | 245710.5263 | 78710.5263 | 0
0
This schedule is built from the WIP tab by one FILTER formula in cell B9 - change a job's Status on the WIP tab and it moves here on its own. Nothing on this tab needs editing.