## WIP
[Company name]
Work-in-Progress Schedule
As of | [period-end date]
No control issues flagged
|  |  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | CURRENT YEAR |  |  | BALANCE SHEET |  | CONTROLS
Job # | Description | Status | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings | Issues
| Totals - all jobs |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| of which In Progress |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
| of which Complete |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
How to use this schedule
Enter | from the job cost report and general ledger
Enter | from the prior-year WIP schedule
Formula | calculated - do not type here
Red text | a control failed - the Issues column at the far right says what is wrong
Status drives the Contracts in Progress and Completed Contracts tabs. Those tabs rebuild themselves - never edit them.
To add jobs: right-click the blank row just above Totals, choose Insert, then copy the formulas down from the row above. Every total, control and tab picks up the new row automatically.
Underbillings and overbillings come from this schedule; the tie-out below compares the schedule to the general ledger.
| Tie-out to the general ledger | [14 empty] | CY revenue | CY cost |  | Underbillings | Overbillings
Balance per general ledger
| Per this schedule (Totals row) | [14 empty] | 0 | 0 |  | 0 | 0
| Difference - must be zero | [14 empty] | 0 | 0 |  | 0 | 0
| Loss contracts in progress |  |  |  | Estimated GP
| Total expected loss on in-progress loss contracts |  |  |  | 0
| Loss already recognized through % complete |  |  |  | 0
| Additional loss to accrue (provision for loss on contracts) |  |  |  | 0
Prepared by Levvigo ¦ levvigo.com

## Contracts in Progress
[Company name]
Schedule of Contracts in Progress
For the period ended [period-end date]
|  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | CURRENT YEAR |  |  | BALANCE SHEET
Job # | Description | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings
| Totals - 0 contracts | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
This schedule is built from the WIP tab by one FILTER formula in cell B9 - change a job's Status on the WIP tab and it moves here on its own. Nothing on this tab needs editing.

## Completed Contracts
[Company name]
Schedule of Completed Contracts
For the period ended [period-end date]
|  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | CURRENT YEAR |  |  | BALANCE SHEET
Job # | Description | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings
| Totals - 0 contracts | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
This schedule is built from the WIP tab by one FILTER formula in cell B9 - change a job's Status on the WIP tab and it moves here on its own. Nothing on this tab needs editing.