## WIP
Sample Contractor
Work-in-Progress Schedule
As of | 5/31/20CY
No control issues flagged
|  |  | ESTIMATE |  |  |  | PROGRESS |  | INCEPTION TO DATE |  |  |  |  | PRIOR YEARS |  | 20CY |  |  | BALANCE SHEET |  | CONTROLS
Job # | Description | Status | Contract Amount | Estimated Cost | Estimated GP | Est. GP % | % Complete | Cost to Complete | Billings | Revenue | Cost | GP | GP % | Revenue | Cost | Revenue | Cost | GP | Underbillings | Overbillings | Issues
J101 | Office Renovation | In Progress | 500000 | 400000 | 100000 | 20% | 70% | 120000 | 330000 | 350000 | 280000 | 70000 | 20% | 150000 | 120000 | 200000 | 160000 | 40000 | 20000 | 0
J102 | Warehouse Addition | In Progress | 800000 | 680000 | 120000 | 15% | 80% | 136000 | 680000 | 640000 | 544000 | 96000 | 15% | 320000 | 272000 | 320000 | 272000 | 48000 | 0 | 40000
J103 | Clinic Fitout | Complete | 300000 | 225000 | 75000 | 25% | 100% | 0 | 300000 | 300000 | 225000 | 75000 | 25% | 150000 | 112500 | 150000 | 112500 | 37500 | 0 | 0
J104 | Retail Shell | In Progress | 600000 | 480000 | 120000 | 20% | 40% | 288000 | 210000 | 240000 | 192000 | 48000 | 20% | 0 | 0 | 240000 | 192000 | 48000 | 30000 | 0
J105 | School Renovation | In Progress | 400000 | 300000 | 100000 | 25% | 50% | 150000 | 225000 | 200000 | 150000 | 50000 | 25% | 0 | 0 | 200000 | 150000 | 50000 | 0 | 25000
J106 | Service Building | Complete | 250000 | 200000 | 50000 | 20% | 100% | 0 | 250000 | 250000 | 200000 | 50000 | 20% | 0 | 0 | 250000 | 200000 | 50000 | 0 | 0
J107 | Equipment Pad | In Progress | 200000 | 150000 | 50000 | 25% | 25% | 112500 | 70000 | 50000 | 37500 | 12500 | 25% | 0 | 0 | 50000 | 37500 | 12500 | 0 | 20000
J108 | Utility Upgrade | In Progress | 150000 | 120000 | 30000 | 20% | 20% | 96000 | 20000 | 30000 | 24000 | 6000 | 20% | 0 | 0 | 30000 | 24000 | 6000 | 10000 | 0
| Totals - all jobs |  | 3200000 | 2555000 | 645000 | 20.16% | 64.68% | 902500 | 2085000 | 2060000 | 1652500 | 407500 | 19.78% | 620000 | 504500 | 1440000 | 1148000 | 292000 | 60000 | 85000
| of which In Progress |  | 2650000 | 2130000 | 520000 | 19.62% | 57.63% | 902500 | 1535000 | 1510000 | 1227500 | 282500 | 18.71% | 470000 | 392000 | 1040000 | 835500 | 204500 | 60000 | 85000
| of which Complete |  | 550000 | 425000 | 125000 | 22.73% | 100% | 0 | 550000 | 550000 | 425000 | 125000 | 22.73% | 150000 | 112500 | 400000 | 312500 | 87500 | 0 | 0
How to use this schedule
Enter | from the job cost report and general ledger
Enter | from the prior-year WIP schedule
Formula | calculated - do not type here
Red text | a control failed - the Issues column at the far right says what is wrong
Status drives the Contracts in Progress and Completed Contracts tabs. Those tabs rebuild themselves - never edit them.
To add jobs: right-click the blank row just above Totals, choose Insert, then copy the formulas down from the row above. Every total, control and tab picks up the new row automatically.
Underbillings and overbillings come from this schedule; the tie-out below compares the schedule to the general ledger.
| Tie-out to the general ledger | [14 empty] | CY revenue | CY cost |  | Underbillings | Overbillings
| Balance per general ledger | [14 empty] | 1440000 | 1148000 |  | 60000 | 85000
| Per this schedule (Totals row) | [14 empty] | 1440000 | 1148000 |  | 60000 | 85000
| Difference - must be zero | [14 empty] | 0 | 0 |  | 0 | 0
| Loss contracts in progress |  |  |  | Estimated GP
| Total expected loss on in-progress loss contracts |  |  |  | 0
| Loss already recognized through % complete |  |  |  | 0
| Additional loss to accrue (provision for loss on contracts) |  |  |  | 0
Prepared by Levvigo ¦ levvigo.com

## Contracts in Progress
Sample Contractor
Schedule of Contracts in Progress
As of 5/31/20CY
|  |  |  | ESTIMATE |  |  |  |  | PROGRESS |  |  | INCEPTION TO DATE | [5 empty] | PRIOR YEARS |  |  | CURRENT YEAR |  |  |  | BALANCE SHEET
Job # | Description |  |  | Contract Amount | Estimated Cost | Estimated GP | Est. GP % |  | % Complete | Cost to Complete |  | Billings | Revenue | Cost | GP | GP % |  | Revenue | Cost |  | Revenue | Cost | GP |  | Underbillings | Overbillings
| Totals - 6 contracts |  |  | 2650000 | 2130000 | 520000 | 19.62% |  | 57.63% | 902500 |  | 1535000 | 1510000 | 1227500 | 282500 | 18.71% |  | 470000 | 392000 |  | 1040000 | 835500 | 204500 |  | 60000 | 85000
J101 | Office Renovation | In Progress | 0 | 500000 | 400000 | 100000 | 20% | 0 | 70% | 120000 | 0 | 330000 | 350000 | 280000 | 70000 | 20% | 0 | 150000 | 120000 | 0 | 200000 | 160000 | 40000 | 0 | 20000 | 0
J102 | Warehouse Addition | In Progress | 0 | 800000 | 680000 | 120000 | 15% | 0 | 80% | 136000 | 0 | 680000 | 640000 | 544000 | 96000 | 15% | 0 | 320000 | 272000 | 0 | 320000 | 272000 | 48000 | 0 | 0 | 40000
J104 | Retail Shell | In Progress | 0 | 600000 | 480000 | 120000 | 20% | 0 | 40% | 288000 | 0 | 210000 | 240000 | 192000 | 48000 | 20% | 0 | 0 | 0 | 0 | 240000 | 192000 | 48000 | 0 | 30000 | 0
J105 | School Renovation | In Progress | 0 | 400000 | 300000 | 100000 | 25% | 0 | 50% | 150000 | 0 | 225000 | 200000 | 150000 | 50000 | 25% | 0 | 0 | 0 | 0 | 200000 | 150000 | 50000 | 0 | 0 | 25000
J107 | Equipment Pad | In Progress | 0 | 200000 | 150000 | 50000 | 25% | 0 | 25% | 112500 | 0 | 70000 | 50000 | 37500 | 12500 | 25% | 0 | 0 | 0 | 0 | 50000 | 37500 | 12500 | 0 | 0 | 20000
J108 | Utility Upgrade | In Progress | 0 | 150000 | 120000 | 30000 | 20% | 0 | 20% | 96000 | 0 | 20000 | 30000 | 24000 | 6000 | 20% | 0 | 0 | 0 | 0 | 30000 | 24000 | 6000 | 0 | 10000 | 0
This schedule is built from the WIP tab by one FILTER formula in cell B9 - change a job's Status on the WIP tab and it moves here on its own. Nothing on this tab needs editing.

## Completed Contracts
Sample Contractor
Schedule of Completed Contracts
As of 5/31/20CY
|  |  |  | ESTIMATE |  |  |  |  | PROGRESS |  |  | INCEPTION TO DATE | [5 empty] | PRIOR YEARS |  |  | CURRENT YEAR |  |  |  | BALANCE SHEET
Job # | Description |  |  | Contract Amount | Estimated Cost | Estimated GP | Est. GP % |  | % Complete | Cost to Complete |  | Billings | Revenue | Cost | GP | GP % |  | Revenue | Cost |  | Revenue | Cost | GP |  | Underbillings | Overbillings
| Totals - 2 contracts |  |  | 550000 | 425000 | 125000 | 22.73% |  | 100% | 0 |  | 550000 | 550000 | 425000 | 125000 | 22.73% |  | 150000 | 112500 |  | 400000 | 312500 | 87500 |  | 0 | 0
J103 | Clinic Fitout | Complete | 0 | 300000 | 225000 | 75000 | 25% | 0 | 100% | 0 | 0 | 300000 | 300000 | 225000 | 75000 | 25% | 0 | 150000 | 112500 | 0 | 150000 | 112500 | 37500 | 0 | 0 | 0
J106 | Service Building | Complete | 0 | 250000 | 200000 | 50000 | 20% | 0 | 100% | 0 | 0 | 250000 | 250000 | 200000 | 50000 | 20% | 0 | 0 | 0 | 0 | 250000 | 200000 | 50000 | 0 | 0 | 0
This schedule is built from the WIP tab by one FILTER formula in cell B9 - change a job's Status on the WIP tab and it moves here on its own. Nothing on this tab needs editing.